## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | Material Requisition To Resource Division |  |  | RTOR000153/2022-2023 | 536/MD | 21/02/2023 | 21/02/2023 | Resource Division | 9.38 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | Sinking of 2 Nos. Tube well & Accommodate FHTC (100 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000110/2023-2024 | 2511/MD | 18/07/2023 | 01/09/2023 | DEBASISH DOGRA | 21.94 | 15.55 | 70.87 | 70
3 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | Laying distribution pipe line under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000103/2023-2024 | 2485/MD | 17/07/2023 | 19/12/2024 | A R ENTERPRISE | 18.49 | 17.66 | 95.5 | 70
4 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | Laying distribution pipe line & Accommodate FHTC (200 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000521/2023-2024 | 5500/MD | 14/12/2023 | 28/01/2024 | MAHARAJA CONSTRUCTION CO. | 43.39 | 31.78 | 73.25 | 40
5 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | New Service connection charges for Pathri w/s scheme, t/w no.-II |  |  | BILL/01967/2023-2024 | 184/JMD | 30/03/2024 | 30/03/2024 | WBSEDCL | 8.52 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | New Service connection charges for Pathri w/s scheme, t/w no.-I |  |  | BILL/01968/2023-2024 | 185/JMD | 30/03/2024 | 30/03/2024 | WBSEDCL | 3.3 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Salbani | Central Drilling | PATHRI AND AJOINING MOUJAS | SM/13807 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 13.03 | 0.06 | 11
8 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | Laying distribution pipe line, Rising main & Accommodate FHTC (400 Nos.) including 2 yrs. O & M under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000148/2023-2024 | 2639/MD | 24/07/2023 | 16/07/2025 | GOUTAM RAY | 138.15 | 43.05 | 31.16 | 70
9 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | Construction of Pump House, Boundary wall & Accommodate FHTC (216 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-F] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000416/2023-2024 | 5152/MD | 07/11/2023 | 31/08/2025 | BISWAS CONSTRUCTION | 45.23 | 0 | 0 | 81
10 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | PATHRI AND AJOINING MOUJAS | SM/13807 | New | Construction of RCC OHR (150 CuM) & Accommodate FHTC (200 Nos.) under JJM with allied work for Pathri PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division |  | ORD/000547/2024-2025 | 738/MD | 19/03/2025 | 15/09/2025 | SAMIT PAL | 83.17 | 0 | 0 | 0
Total | [13 empty] | 21711.32 | 121.06 | 0.56