## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | NANASOL AND ADJOINING MOUJAS PWSS | SM/13808 | New | Material Requisition To Resource Division |  |  | RTOR000266/2023-2024 | 2224/MD | 15/06/2023 | 15/06/2023 | Resource Division | 20.41 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | NANASOL AND ADJOINING MOUJAS PWSS | SM/13808 | New | Sinking of Tube Well ,Laying of Rising Main ,Laying distribution pipe line, Pump House , Boundary Wall , soil investigation , 100 cum OHR( Torch type with solid raft ) & Accommodate FHTC (529 Nos.) including 2 years operation & maintenance under JJM with allied work for Nanasol & its adjoining mouzas W/S scheme in Salbani Block including supply of all labour & materials within Medinipur Sadar Sub-division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000390/2023-2024 | 5064/MD | 26/10/2023 | 23/04/2024 | ASHIM KUMAR DEY | 218.49 | 16.22 | 7.42 | 15
3 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | NANASOL AND ADJOINING MOUJAS PWSS | SM/13808 | New | New service connection charges for Nonasol w/s scheme, t/w no.II |  |  | BILL/01376/2023-2024 | 39/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 2.29 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | NANASOL AND ADJOINING MOUJAS PWSS | SM/13808 | New | New service connection charges for Nonasole w/s scheme, t/w no.I |  |  | BILL/01375/2023-2024 | 38/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 5.62 | 0 | 0 | 0
Total | [13 empty] | 246.8 | 16.22 | 6.57