## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. | SM/13822 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Kalaikunda, Block - Kharagpur-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/001141/2020-2021 | 67/MD | 11/01/2021 | 21/01/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.52 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. | SM/13822 | Augmentation | Electric Quotation for KALAIKUNDA Water Supply Scheme T/W-I (Ref. ID-212248275) |  |  | BILL/01688/2023-2024 | BP-2023-24-174 | 04/08/2023 | 04/08/2023 | WBSEDCL | 0.95 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. | SM/13822 | Augmentation | Laying distribution pipe line, Soil test, FHTC & Construction of R.C.C. Over Head Reservoir of capacity 300 Cum and staging height 20.00 mtr. with allied work for Augmentation of Kalaikunda W/S Scheme in Kharagpur-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang),JE3 Kharagpur Sub-division | ORD/000010/2022-2023 | 2411/MD | 25/11/2022 | 30/05/2025 | ASHIM KUMAR DEY | 226.86 | 0 | 0 | 69
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. | SM/13822 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000013/2023-2024 | 1129/W/MMD | 12/04/2023 | 09/10/2023 | P.K.ENGINEERING | 23.75 | 0 | 0 | 70
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. | SM/13822 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2024-2025 | 3418/MD | 25/11/2024 | 25/11/2024 | Resource Division | 14.5 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Kalaikunda to Accommodate FHTC, Block - Kharagpur-I, District - Paschim Medinipur. | SM/13822 | Augmentation | Cleaning the chokage of pipe in the existing line at Kalaikunda PWSS under Kharagpur Sub-Division of Midnapur Division, P.H.E Dte. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000339/2024-2025 | 3582/MD | 06/12/2024 | 05/01/2025 | M/S. GEO | 4.56 | 0 | 0 | 100
Total | [13 empty] | 274.15 | 0 | 0