## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/13823 | Augmentation | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Tap Connection of existing PWSS (Birsingha, Block - Ghatal) to be Augmentation / Rejuvenation under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000121/2021-2022 | 1011/MD | 25/06/2021 | 05/07/2021 | RISHAN ENGINEERING CONSULTANCY | 3.25 | 2.67 | 81.96 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/13823 | Augmentation | Special Exigent Repair of Head work site & its adjoining structures of Birsingha W/S Scheme in consultation with district administration in the model village of Birsingha (Birth place of Iswarchandra Vidyasagar) under Ghatal Sub-Division of Midnapore Division, PHE Dte. [PHASE-II] | AE Ghatal Sub-division |  | ORD/000669/2022-2023 | 722/MD | 09/03/2023 | 30/03/2023 | PULLOCK KUMAR GHOSH | 14.3 | 10.87 | 75.98 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/13823 | Augmentation | Special Exigent Repair of Head work site & its adjoining structures of Birsingha W/S Scheme in consultation with district administration in the model village of Birsingha (Birth place of Iswarchandra Vidyasagar) under Ghatal Sub-Division of Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000536/2022-2023 | 2605/MD | 20/12/2022 | 04/01/2023 | HIRAK KUMAR GHOSH | 9.99 | 9.98 | 99.86 | 94
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/13823 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000205/2023-2024 | 1421/MD | 04/05/2023 | 04/05/2023 | Resource Division | 18.02 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/13823 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001593/2022-2023 | 475/W/MMD | 20/03/2023 | 16/09/2023 | S.B.ENTERPRISE | 10.98 | 10.39 | 94.65 | 100
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/13823 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2024-2025 | 3366/MD | 25/11/2024 | 25/11/2024 | Resource Division | 0.83 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/13823 | Augmentation | Laying additional pipe line, interconnection, FHTC & other allied works for continuation of laying distribution system, sinking of tube well, FHTC for Augmentation of Birsingha W/S Scheme within Ghatal block of Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000638/2023-2024 | 138/MD | 18/01/2024 | 22/02/2025 | DIPAK KUMAR BAKLY | 29.75 | 21.17 | 71.16 | 90
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Birsingha to Accommodate FHTC under Jal Jeevan Mission under Ghatal Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/13823 | Augmentation | Laying distribution pipeline, providing FHTC including Sinking of 250mm X 150mm X 190 m deep tube well for Augmentation of Birsingha Water Supply Scheme within Ghatal block under Ghatal Sub-Division of Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Ghatal) | ORD/000501/2022-2023 | 2412/MD | 25/11/2022 | 09/12/2024 | DIPAK KUMAR BAKLY | 91 | 24.88 | 27.34 | 90
Total | [13 empty] | 178.12 | 79.96 | 44.89