## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | SM/13826 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR location for Augmentation of Chak Ismailpur W/S Scheme under Dantan-I Block of Paschim Medinipur District through Jadavpur University. | AE/RWS Midnapore Sub Division |  | ORD/000732/2022-2023 | 706/MD | 06/03/2023 | 13/03/2023 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | SM/13826 | Augmentation | Laying Rising main pipe line, Construction of Pump House & Boundary wall under JJM with allied work for Augmentation Chak Ismailpur PWSS in Dantan-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000349/2023-2024 | 4023/MD | 10/10/2023 | 09/12/2023 | TARUN MAHATA | 24.51 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | SM/13826 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Chak Ismailpur, Block - Dantan-I) to be Augmentation / Rejuvenation under Midnapore Division P.H.E. Dte. | AE/RWS Midnapore Sub Division |  | ORD/000917/2020-2021 | 246/DP/MD | 10/02/2021 | 20/02/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 2.77 | 2.62 | 94.56 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | SM/13826 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 94/MD | 10/01/2023 | 10/01/2023 | Resource Division | 16.53 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | SM/13826 | Augmentation | Quatation for New service connection at Chakismilpur(Ref no-203987606) |  |  | BILL/00114/2023-2024 | BP-2023-24-65 | 06/06/2023 | 06/06/2023 | WBSEDCL | 5.42 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | SM/13826 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001511/2022-2023 | 355/W/MMD | 09/03/2023 | 05/09/2023 | MANORANJAN DEY | 11.44 | 8.34 | 72.9 | 20
7 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Chak Ismailpur to Accommodate FHTC, Block - Dantan-I, District - Paschim Medinipur. | SM/13826 | Augmentation | Sinking of 250 X 150 mm dia. X 200 Mtr. Depth tube well, Laying distribution pipe line, Soil test & Construction of R.C.C. Over Head Reservoir of capacity 100 Cum and staging height 20.00 mtr. & FHTC (853 Nos.) under JJM with allied work for Augmentation of Chak Ismailpur and its adjoining mouzas W/S scheme in Datan-I Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division( Dantan-I) | ORD/000630/2022-2023 | 455/MD | 13/02/2023 | 14/11/2025 | M/S. D.K.H.CONSTRUCTION | 200.6 | 138.03 | 68.81 | 82
Total | [13 empty] | 266.05 | 148.99 | 56