## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | MURAKATI AND ADJOINING MOUJAS PWSS | SM/14004 | New | Material Requisition To Resource Division |  |  | RTOR000107/2023-2024 | 1241/MD | 27/04/2023 | 27/04/2023 | Resource Division | 24.53 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | MURAKATI AND ADJOINING MOUJAS PWSS | SM/14004 | New | Payment for WBSEDCL new connection at MURAKATI 2 (SM/14004. MURAKATI AND ADJOINING MOUJAS PWSS ) |  |  | BILL/00369/2024-2025 | 170/JMD | 07/06/2024 | 07/06/2024 | WBSEDCL | 4.23 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | MURAKATI AND ADJOINING MOUJAS PWSS | SM/14004 | New | WBSEDCL new connection payment for Murakati t/w 1 |  |  | BILL/00082/2024-2025 | 56/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 8.25 | 0 | 0 | 0
Total | [13 empty] | 37.01 | 0 | 0