## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 11/06/2023 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
2 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Material Requisition To Resource Division |  |  | RTOR000264/2023-2024 | 2040/MD | 18/05/2023 | 18/05/2023 | Resource Division | 26.77 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BULANPUR AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001959/2022-2023 | 871/W/MMD | 27/03/2023 | 23/09/2023 | KUSHANI ENTERPRISE | 5.98 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Laying distribution pipe line & Accommodate FHTC (200 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000433/2023-2024 | 5189/MD | 08/11/2023 | 23/12/2023 | A.K. SIKDAR | 47.78 | 0 | 0 | 70
5 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Laying of Rising main, Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (400 Nos.) including 2 years operation & maintenance under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000418/2023-2024 | 5154/MD | 07/11/2023 | 06/01/2024 | SAIKAT DANDAPAT | 111.63 | 0 | 0 | 3
6 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Sinking of 2 (Two) Nos. Tube well for Bulanpur & its adjoining mouzas (Zone-I) PWSS in Garhbeta-II block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000138/2023-2024 | 2622/MD | 24/07/2023 | 23/08/2023 | M/S BISWANATH CONSTRUCTION | 17.57 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | New service connection |  |  | BILL/01301/2023-2024 | 72/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.72 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | New service connection |  |  | BILL/01302/2023-2024 | 73/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.14 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Garbeta-II | Central Drilling | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
10 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Laying distribution pipe line & Accommodate FHTC (202 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000174/2023-2024 | 2676/MD | 26/07/2023 | 16/07/2025 | NIMAI HAZRA | 33.52 | 0 | 0 | 70
11 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Sinking of Tube well, Laying distribution pipe line, Boundary wall, Pump House alongwith 20 CuM OHR (Zone-2) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme with Standalone in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000175/2023-2024 | 2677/MD | 26/07/2023 | 12/11/2025 | ANNAPURNA TUBEWELL WORKS | 36.74 | 0 | 0 | 15
12 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | BULANPUR AND ADJOINING MOUJAS PWSS | SM/14031 | New | Construction of 150 CuM OHR (Torch type with Solid raft) (Zone-1) & Accommodate FHTC (300 Nos.) under JJM with allied work for Bulanpur & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division |  | ORD/000540/2024-2025 | 731/MD | 18/03/2025 | 14/09/2025 | DEVJYOTI BERA | 88.31 | 0 | 0 | 0
Total | [13 empty] | 21825.85 | 0 | 0