## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | Construction of Boundary wall & Accommodate FHTC (200 Nos.) under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000219/2023-2024 | 2872/MD | 10/08/2023 | 24/09/2023 | DEBJIT PATRA | 16.83 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | Construction of 250 cum OHR (Intze type with solid raft) & Accommodate FHTC (526 Nos.) under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division |  | ORD/000335/2024-2025 | 3578/MD | 06/12/2024 | 04/06/2025 | A R CONSTRUCTION | 111.83 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | Sinking of 1 (One) Nos. Tube well for Mahasol & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. (Part-II) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000113/2023-2024 | 2514/MD | 18/07/2023 | 02/08/2023 | BADAL CHANDRA MAIKAP | 8.13 | 7.49 | 92.06 | 100
4 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | Sinking of 2 (Two) Nos. Tube well for Mahasol & its adjoining mouzas PWSS in Salboni block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. (Part-I) | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000220/2023-2024 | 2873/MD | 10/08/2023 | 09/09/2023 | DEBJIT PATRA | 16.28 | 14.65 | 89.95 | 100
5 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | Material Requisition To Resource Division |  |  | RTOR000070/2024-2025 | 3388/MD | 25/11/2024 | 25/11/2024 | Resource Division | 9.4 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | New service connection charges for Mahasol, t/w-II w/s scheme |  |  | BILL/01307/2023-2024 | 78/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.38 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | New service connection charges for Mahasol, t/w-I w/s scheme |  |  | BILL/01309/2023-2024 | 80/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.03 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Salbani | Central Drilling | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 33.09 | 0.16 | 11
9 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | MAHASOL AND ADJOINING MOUJAS PWSS | SM/14036 | New | Laying Rising main, distribution pipe line, 2 nos. Pump House, Boundary wall & Accommodate FHTC (800 Nos.) including 2 years operation & maintenance under JJM with allied work for Mahasol & its adjoining mouzas W/S Scheme in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000177/2023-2024 | 2717/MD | 31/07/2023 | 23/08/2025 | M/S. D.K.H.CONSTRUCTION | 241.48 | 180.88 | 74.9 | 40
Total | [13 empty] | 21751.13 | 236.1 | 1.09