## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | GARMAL AND ADJOINING MOUJAS PWSS | SM/14090 | New | Material Requisition To Resource Division |  |  | RTOR000156/2022-2023 | 539/MD | 21/02/2023 | 21/02/2023 | Resource Division | 14 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | GARMAL AND ADJOINING MOUJAS PWSS | SM/14090 | New | New Service Connection Charges for Garmal T/W - I PWSS |  |  | BILL/01028/2024-2025 | 359/JMD | 20/09/2024 | 20/09/2024 | WBSEDCL | 8.11 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Central Drilling | GARMAL AND ADJOINING MOUJAS PWSS | SM/14090 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
4 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | GARMAL AND ADJOINING MOUJAS PWSS | SM/14090 | New | Laying distribution pipe line, Rising main & Accommodate FHTC (250 Nos.) including 2 yrs. O & M under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000004/2024-2025 | 1837/MD | 12/06/2024 | 05/12/2025 | S.T. ENTERPRISE | 141.14 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | GARMAL AND ADJOINING MOUJAS PWSS | SM/14090 | New | Sinking of Tube well, Laying distribution pipe line, Pump House & Accommodate FHTC (300 Nos.) under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000850/2023-2024 | 827/MD | 15/03/2024 | 04/01/2026 | MIDNAPUR PIPE CONCERN | 75.01 | 0 | 0 | 40
6 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | GARMAL AND ADJOINING MOUJAS PWSS | SM/14090 | New | Construction of RCC OHR (150 CuM), Boundary wall & Accommodate FHTC (400 Nos.) under JJM with allied work for Garmal PWSS in Salboni block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division | JE2 Sadar Sub-division | ORD/000306/2024-2025 | 3402/MD | 25/11/2024 | 20/11/2025 | S.T. ENTERPRISE | 113.63 | 0 | 0 | 0
Total | [13 empty] | 21691.64 | 0 | 0