## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ranichak & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000927/2021-2022 | 497/MD | 15/03/2022 | 04/04/2022 | GOBINDA MAITY | 6.21 | 5.81 | 93.65 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ramkrishnapur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000090/2022-2023 | 666/MD | 08/04/2022 | 28/04/2022 | SIRCON ENGINEERING SERVICES | 7.11 | 6.67 | 93.82 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Krishnapur & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000095/2022-2023 | 1007/MD | 27/05/2022 | 16/06/2022 | SIRCON ENGINEERING SERVICES | 7.38 | 6.75 | 91.55 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Khandanga & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000097/2022-2023 | 1017/MD | 27/05/2022 | 16/06/2022 | SIRCON ENGINEERING SERVICES | 7.91 | 6.35 | 80.23 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Mahespur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000111/2022-2023 | 1022/MD | 30/05/2022 | 19/06/2022 | SIRCON ENGINEERING SERVICES | 5.27 | 5.27 | 100 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Piardanga & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000099/2022-2023 | 1019/MD | 27/05/2022 | 16/06/2022 | SIRCON ENGINEERING SERVICES | 5.88 | 5.52 | 94.01 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Chanipat & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000094/2022-2023 | 674/MD | 11/04/2022 | 01/05/2022 | GOBINDA MAITY | 9.45 | 9.35 | 98.92 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Haridharpur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000112/2022-2023 | 1023/MD | 30/05/2022 | 19/06/2022 | SIRCON ENGINEERING SERVICES | 6.92 | 6.92 | 100 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jot Kanuramgar & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000912/2021-2022 | 511/MD | 16/03/2022 | 05/04/2022 | SIRCON ENGINEERING SERVICES | 7.13 | 5.76 | 80.72 | 0
10 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kalla & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000096/2022-2023 | 1016/MD | 27/05/2022 | 16/06/2022 | SIRCON ENGINEERING SERVICES | 6.87 | 6.87 | 100 | 0
11 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jadabpur & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000114/2022-2023 | 685/MD | 12/04/2022 | 02/05/2022 | GOBINDA MAITY | 10.25 | 8.88 | 86.63 | 0
12 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Manikkundu & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000113/2022-2023 | 684/MD | 12/04/2022 | 02/05/2022 | GOBINDA MAITY | 6.02 | 6.02 | 100.02 | 0
13 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Ramkrishnapur & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000911/2021-2022 | 510/MD | 16/03/2022 | 05/04/2022 | SIRCON ENGINEERING SERVICES | 6.64 | 4.07 | 61.3 | 0
14 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Purshuri & its adjoining Mouzas PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000092/2022-2023 | 668/MD | 08/04/2022 | 28/04/2022 | SIRCON ENGINEERING SERVICES | 6.25 | 6.25 | 100 | 0
15 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Benai & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000115/2022-2023 | 686/MD | 12/04/2022 | 02/05/2022 | GOBINDA MAITY | 10.01 | 8.83 | 88.27 | 0
16 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Garurna & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000118/2022-2023 | 690/MD | 13/04/2022 | 03/05/2022 | GOBINDA MAITY | 9.65 | 9.65 | 100 | 0
17 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kashinathpur & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000119/2022-2023 | 691/MD | 13/04/2022 | 03/05/2022 | GOBINDA MAITY | 5.48 | 5.24 | 95.53 | 0
18 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Khukudaha & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000120/2022-2023 | 692/MD | 13/04/2022 | 03/05/2022 | GOBINDA MAITY | 7.69 | 6.79 | 88.31 | 0
19 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Katina & its adjoining Mouzas PWSS, Block - Sabang under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000121/2022-2023 | 693/MD | 13/04/2022 | 03/05/2022 | GOBINDA MAITY | 10.1 | 10.1 | 100 | 0
20 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Uttar Bar & its adjoining Mouzas PWSS, Block - Daspur-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-II) | ORD/000116/2022-2023 | 688/MD | 13/04/2022 | 03/05/2022 | GOBINDA MAITY | 11.78 | 9.82 | 83.32 | 0
21 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sagarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000104/2022-2023 | 1054/MD | 02/06/2022 | 22/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.35 | 4.35 | 100 | 0
22 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Tatarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000107/2022-2023 | 1062/MD | 02/06/2022 | 22/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 7.2 | 7.2 | 100 | 0
23 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Suratpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000108/2022-2023 | 1063/MD | 02/06/2022 | 22/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.99 | 4.99 | 100 | 0
24 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kenchkapur & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000548/2022-2023 | 2679/MD | 30/12/2022 | 19/01/2023 | SIRCON ENGINEERING SERVICES | 6.25 | 5.98 | 95.69 | 0
25 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Bandipur & its adjoining Mouzas PWSS AND (2) Dhanyagachhi & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000549/2022-2023 | 2680/MD | 30/12/2022 | 29/01/2023 | SIRCON ENGINEERING SERVICES | 9.89 | 9.89 | 100 | 0
26 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of 3 (Three) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Gohaldanga & its adjoining Mouzas PWSS (2) Pirchak & its adjoining Mouzas PWSS & (3) Dwarkhola Mouza Stand Alone PWSS, Block - Chandrakona-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-I) | ORD/000544/2022-2023 | 2675/MD | 30/12/2022 | 13/02/2023 | SIRCON ENGINEERING SERVICES | 6.19 | 6.19 | 100 | 0
27 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Hrisingpur & its adjoining Mouzas PWSS AND (2) Dhunrabila & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000545/2022-2023 | 2676/MD | 30/12/2022 | 29/01/2023 | SIRCON ENGINEERING SERVICES | 7.92 | 7.92 | 100 | 0
28 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Kuapur & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000546/2022-2023 | 2677/MD | 30/12/2022 | 19/01/2023 | SIRCON ENGINEERING SERVICES | 6.18 | 6.12 | 98.98 | 0
29 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Jhakra & its adjoining Mouzas PWSS, Block - Chandrakona-II under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(CK-II) | ORD/000547/2022-2023 | 2678/MD | 30/12/2022 | 19/01/2023 | SIRCON ENGINEERING SERVICES | 5.8 | 5.8 | 100 | 0
30 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 108; 110; 111; 116; 118; 119; 120; 121; 122; 123; 124; 125; 197; 198; 199; 200; 201; 202; 206; 207 ;208 ;209] (Population as per 2011 Census: 18,226) [PART-II] | AE Kharagpur Sub-division |  | ORD/000486/2022-2023 | 1601/MD | 02/08/2022 | 22/08/2022 | GOBINDA MAITY | 10.54 | 9.34 | 88.65 | 0
31 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 12; 13; 14; 15; 16; 17; 18; 19; 20; 21; 22; 23; 24; 25; 26; 27; 28; 29; 30; 31; 32; 33; 34; 35; 36; 37; 38; 39; 40; 41; 42; 45 (50%); 46; 47; 48; 49; 50; 51; 52; 53; 54; 56; 65; 67] (Population as per 2011 Census : 18,719) [PART-III] | AE Kharagpur Sub-division |  | ORD/000487/2022-2023 | 1602/MD | 02/08/2022 | 22/08/2022 | GOBINDA MAITY | 10.82 | 10.82 | 100 | 0
32 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 184; 246; 247; 254; 255; 256; 257; 258; 259; 260; 261; 262; 263] (Population as per 2011 Census: 14,366) [PART-V] | AE Kharagpur Sub-division |  | ORD/000489/2022-2023 | 1604/MD | 02/08/2022 | 22/08/2022 | GOBINDA MAITY | 8.31 | 7.12 | 85.68 | 0
33 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 1; 2; 3; 4; 5; 6; 7; 8; 9; 10; 11; 55; 57; 58; 59; 60; 61; 62; 63; 89; 90; 91; 92; 93; 94; 95; 96; 97; 98; 99; 100; 101; 102; 103; 104; 105; 106; 107; 108; 109; 110; 111; 112; 113; 114; 115; 117; 126; 127; 128; 129; 130; 134; 136; 137; 138 & 139] (Population as per 2011 Census : 30,848) | AE Kharagpur Sub-division |  | ORD/000495/2022-2023 | 2062/MD | 30/09/2022 | 15/10/2022 | GOBINDA MAITY | 17.83 | 13.89 | 77.87 | 0
34 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 45(50%), 43, 44, 87, 149, 66; 85; 86; 145; 146; 147; 148; 150; 152; 153; 185; 187] (Population as per 2011 Census : 13,852) [PART-VIII] | AE Kharagpur Sub-division |  | ORD/000492/2022-2023 | 1693/MD | 16/08/2022 | 30/09/2022 | GOBINDA MAITY | 7.52 | 7.51 | 99.83 | 0
35 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 211; 212; 213; 214; 215; 228; 229; 230; 231] (Population as per 2011 Census: 8,961) [PART-I] | AE Kharagpur Sub-division |  | ORD/000485/2022-2023 | 1600/MD | 02/08/2022 | 22/08/2022 | GOBINDA MAITY | 5.18 | 5.18 | 100 | 0
36 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 156; 157; 158; 159; 160; 161; 162; 163; 164; 165; 166; 167; 168; 169; 170; 171; 172; 174; 177; 178; 179; 180; 181; 182; 183] (Population as per 2011 Census : 16,311) [PART-IV] | AE Kharagpur Sub-division |  | ORD/000488/2022-2023 | 1603/MD | 02/08/2022 | 22/08/2022 | GOBINDA MAITY | 9.43 | 9.21 | 97.63 | 0
37 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 337; 338; 339; 340; 341; 342; 343; 344; 273; 274; 275 & 248; 249; 250; 251; 252; 253; 290; 291; 292; 293; 294; 295; 296; 297; 298; 299; 300; 301; 333; 334; 335; 336] (Population as per 2011 Census 15,869) [PART-VI] | AE Kharagpur Sub-division |  | ORD/000490/2022-2023 | 1605/MD | 02/08/2022 | 01/09/2022 | GOBINDA MAITY | 9.17 | 9.17 | 100 | 0
38 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed below mention list of command area within Kharagpur-I block under Midnapore Division, PHE Dte. [Jurisdiction of Command area : J.L. Nos. 69; 70; 71; 72; 73; 74; 75; 76; 77; 78; 79; 80; 81; 82; 83; 84; 154; 155; 173; 175; 176 & 264; 265; 266; 267; 268; 269; 270; 271; 272; 276; 277; 278; 279; 280; 281; 282; 283; 284; 285; 286; 287; 288; 289] (Population as per 2011 Census: 16,781) [PART-VII] | AE Kharagpur Sub-division |  | ORD/000491/2022-2023 | 1692/MD | 16/08/2022 | 15/09/2022 | GOBINDA MAITY | 9.7 | 9.7 | 100 | 0
39 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Bar Kashimpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Makarampur & its adjoining Mouzas PWSS instead of Bar Kashimpur & its adjoining Mouzas PWSS] | AE Ghatal Sub-division |  | ORD/000106/2022-2023 | 1061/MD | 02/06/2022 | 22/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 6.26 | 6.26 | 100 | 0
40 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Rabidaspur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of proposed PWSS - (1) Rabidaspur & its adjoining Mouzas PWSS, (2) Tiorberya & its adjoining Mouzas PWSS & (3) Ramchandrapur & its adjoining Mouzas PWSS instead of Rabidaspur & its adjoining Mouzas PWSS]. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000110/2022-2023 | 1066/MD | 02/06/2022 | 22/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 4.72 | 4.72 | 100 | 0
41 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Preparation of D.P.R (Consultancy work) in connection with the functional house hold connection Proposed Dadpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. [Name of Proposed PWSS Gopalnagar & its adjoining Mouzas PWSS instead of Dadpur & its adjoining Mouzas PWSS] |  |  | BILL/00880/2023-2024 | BP-2023-24-376 | 10/10/2023 |  | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.01 | 0 | 0 | 0
42 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Suratpur & its adjoining Mouzas PWSS Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000746/2022-2023 | 1264/MD | 23/06/2022 | 03/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 1.35 | 1.35 | 100 | 100
43 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Sagarpur & its adjoining Mouzas PWSS, Block - Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE RWS Ghatal Sub-Division(Daspur-I) | ORD/000749/2022-2023 | 1268/MD | 23/06/2022 | 03/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.48 | 0.48 | 100 | 100
44 | PASCHIM MEDINIPUR |  | Midnapore Division | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERED RURAL AREA OF PASCHIM MEDINIPUR DISTRICT IN WEST BENGAL | SM/14107 | Support-M&E | Continuation Work Order for Balance work of Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for proposed Makrampur & its adjoining Mouzas PWSS instead Kashimpur & its adjoining Mouzas PWSS, Block ¿ Daspur-I under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000765/2022-2023 | 1261/MD | 23/06/2022 | 03/07/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 0.34 | 0.34 | 100 | 100
Total | [13 empty] | 314.44 | 294.45 | 93.64