## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14131 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Radhanagr & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000658/2022-2023 | 1756/MD | 24/08/2022 | 13/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.12 | 5.8 | 94.65 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14131 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001646/2022-2023 | 589/W/MMD | 20/03/2023 | 06/04/2025 | K.S.P. ENTERPRISE | 25.24 | 0 | 0 | 80
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14131 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 350 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,711 nos.) under JJM with allied work for Radhanagar PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000347/2023-2024 | 3999/MD | 06/10/2023 | 27/03/2026 | M/S PRADIP KUMAR PAL | 748.96 | 81.85 | 10.93 | 15
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14131 | New | Material Requisition To Resource Division |  |  | RTOR000037/2024-2025 | 3364/MD | 25/11/2024 | 25/11/2024 | Resource Division | 16.7 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14131 | New | QUOTATION MONEY FOR RADHANAGAR WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14131, APPLICATION NO 2004759835, REFERENCE ID 204321895, BIRSINGHA CCC, WBSEDCL |  |  | BILL/01169/2024-2025 | BP-2024-25-302 | 18/06/2024 | 18/06/2024 | WBSEDCL | 6.7 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14131 | New | QUOTATION MONEY FOR RADHANAGAR WATER SUPPLY SCHEME, T W NO I JJM WORKS, SCHEME CODE SM/14131, APPLICATION NO 2004759827, REFERENCE ID 204321839, BIRSINGHA CCC, WBSEDCL |  |  | BILL/01168/2024-2025 | BP-2024-25-303 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.19 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Radhanagar & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14131 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-04-2025 to 28-09-2025 (Vehicle No. WB06N 8474) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002214/2024-2025 | 432/MMSD-I | 26/03/2025 | 23/09/2025 | S.K.ENTERPRISE | 4.11 | 0 | 0 | 0
Total | [13 empty] | 813.02 | 87.65 | 10.78