## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14478 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000072/2022-2023 | 92/MD | 10/01/2023 | 10/01/2023 | Resource Division | 4.88 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14478 | Augmentation | Electric quotation bill for Tw no-III of Chhotokhelna water supply scheme.Ref Consumer ID-204084641. |  |  | BILL/02517/2023-2024 | BP-2023-24-248 | 14/09/2023 | 14/09/2023 | WBSEDCL | 5.48 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14478 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Chhota Khelna PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000273/2022-2023 | 548/AE/KSD | 23/08/2022 | 22/09/2022 | GOBINDA MAITY | 3.31 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14478 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001609/2022-2023 | 488/W/MMD | 20/03/2023 | 16/09/2023 | KUSHANI ENTERPRISE | 10.98 | 0 | 0 | 50
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14478 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000092/2024-2025 | 3419/MD | 25/11/2024 | 25/11/2024 | Resource Division | 23.16 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Chhotokhelna & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14478 | Augmentation | Disinfection of different type of spot sources at flood affected area of Sultanpur GP. Of Ghatal Block within Ghatal Sub-Division, under Midnapore Division PHE. Dte. In the District of Paschim Medinipur. (Period for ¿July & August-2021) | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/001077/2021-2022 | 559/AE/GSD | 06/08/2021 | 11/08/2021 | SANJIT SINHA | 2.47 | 0 | 0 | 100
Total | [13 empty] | 50.29 | 0 | 0