## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14479 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Karkai PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000274/2022-2023 | 549/AE/KSD | 23/08/2022 | 22/09/2022 | GOBINDA MAITY | 3.06 | 2.95 | 96.52 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14479 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001613/2022-2023 | 534/W/MMD | 20/03/2023 | 09/03/2025 | DEBJYOTI BASU | 11.39 | 7.12 | 62.5 | 20
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14479 | Augmentation | Continuation Work Order for the work of Laying balance distribution pipe line for Augmentation of Karkai & its adjoining mouzas Pipe Water Supply Scheme under Pingla Block within Midnapore Division, P.H.E. Dte. (Total Length = 4,100.00 Mtr.) | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000741/2022-2023 | 845/MD | 24/03/2023 | 31/12/2024 | GOBINDA MAITY | 26.29 | 25.31 | 96.29 | 98
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14479 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary wall to accommodate FHTC (327 Nos.) for Augmentation of Karkai PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000629/2022-2023 | 454/MD | 13/02/2023 | 24/05/2025 | GOBINDA MAITY | 309.44 | 262.77 | 84.92 | 90
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14479 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 113/MD | 10/01/2023 | 10/01/2023 | Resource Division | 1.26 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14479 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000093/2024-2025 | 3420/MD | 25/11/2024 | 25/11/2024 | Resource Division | 16.87 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14479 | Augmentation | ELECTRIC QUOTATION BILL FOR AD TW NO-III OF KARKAI PWSS. REF CONSUMER ID-204350044, APPLICATION NO-2004810203, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA |  |  | BILL/01472/2024-2025 | C072443773813 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.17 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Karkai & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14479 | Augmentation | Laying balance Distribution pipeline for Augmentation of Karkai PWSS under Pingla block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000002/2025-2026 | 917/MD | 08/04/2025 | 22/06/2025 | SUBRATA KUMAR BERA | 71.62 | 0 | 0 | 45
Total | [13 empty] | 443.11 | 298.16 | 67.29