## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14480 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Raghunath chak PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000277/2022-2023 | 552/AE/KSD | 23/08/2022 | 22/09/2022 | GOBINDA MAITY | 2.36 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14480 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000173/2023-2024 | 1371/MD | 02/05/2023 | 02/05/2023 | Resource Division | 6.5 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14480 | Augmentation | Electric Quotation for ADD Tw No-III of Raghunathchak w/s scheme.(Consumer ID-203972934) |  |  | BILL/00081/2023-2024 | BP-2023-24-27 | 04/05/2023 | 04/05/2023 | WBSEDCL | 2.53 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14480 | Augmentation | Laying additional distribution pipeline to accommodate FHTC & allied work for Raghunath Chak PWSS under Pingla block within Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000328/2024-2025 | 3571/MD | 06/12/2024 | 04/02/2025 | SANJIT SINHA | 34.47 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14480 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001713/2022-2023 | 615/W/MMD | 20/03/2023 | 16/09/2023 | CHAKRABORTY MINING & ENGINEERING | 10.78 | 0 | 0 | 80
6 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Raghunath Chak & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14480 | Augmentation | Sinking of Tube well, Laying distribution pipe line, Pump House, Balance FHTC (109) & Repair of Pump House & for Augmentation of Raghunathchak PWSS in Pingla block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE1 Kharagpur Sub-division | ORD/000626/2022-2023 | 451/MD | 13/02/2023 | 02/01/2025 | MASUM ALI KHAN | 95 | 0 | 0 | 82
Total | [13 empty] | 151.64 | 0 | 0