## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14481 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection for Rejuvination / Augmentation of existing Ragpur PWSS Within Pingla Block under Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000276/2022-2023 | 551/AE/KSD | 23/08/2022 | 22/09/2022 | GOBINDA MAITY | 2.88 | 2.88 | 100 | 0
2 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14481 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001943/2022-2023 | 829/W/MMD | 24/03/2023 | 13/03/2025 | M/S EMMESS | 11.33 | 9.71 | 85.76 | 20
3 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14481 | Augmentation | Sinking of Tube Well, Laying distribution pipe line, Pump House, Balance FHTC (211 Nos.) & Repair of Boundary Wall, Pump House & 250 cum OHR for Augmentation of Ragpur PWSS in Pingla Block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(Pingla) | ORD/000255/2023-2024 | 3150/MD | 29/08/2023 | 25/07/2026 | M/S R.N. ENTERPRISE | 339.04 | 234.51 | 69.17 | 60
4 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14481 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2022-2023 | 96/MD | 10/01/2023 | 10/01/2023 | Resource Division | 2.56 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR |  | Midnapore Division | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14481 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000094/2024-2025 | 3421/MD | 25/11/2024 | 25/11/2024 | Resource Division | 14.91 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Augmentation of Ground Based Pipe Water Supply Scheme for Ragpur & its adj. mouzas, Block - Pingla, Dist.- Paschim Medinipur. | SM/14481 | Augmentation | ELECTRIC QUOTATION BILL FOR AD TW NO-III OF RAGPUR PWSS. REF CONSUMER ID-204391667, APPLICATION NO-2004886583, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-PINGLA CCC, NAME OF BLOCK-PINGLA. |  |  | BILL/02427/2024-2025 | BP-2024-25-680 | 27/09/2024 | 27/09/2024 | WBSEDCL | 6.23 | 0 | 0 | 0
Total | [13 empty] | 376.94 | 247.1 | 65.55