## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001745/2022-2023 | 650/W/MMD | 20/03/2023 | 16/09/2023 | M/S. SAJAHAN CHOWDHURY | 43.15 | 27.18 | 62.99 | 63
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Installation of 250mm X 150mm X 150 Mtr. Depth Rig bore Tube well (2 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000078/2023-2024 | 2425/MD | 13/07/2023 | 03/08/2023 | MIDNAPUR PIPE CONCERN | 15.62 | 13.13 | 84.09 | 100
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Installation of 250mm X 150mm X 150 Mtr. Depth Rig bore Tube well (2 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000164/2023-2024 | 2640/MD | 24/07/2023 | 14/08/2023 | MIDNAPUR PIPE CONCERN | 15.62 | 14 | 89.62 | 100
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 1365/MD | 02/05/2023 | 02/05/2023 | Resource Division | 36.92 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GERIASULI-II] WATER SUPPLY ASCHEME [ APPLICATION --2004479502, REFERENCE ID ----204122241, NIMPURA CCC, QUOTATION NO ---2004479502/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GERIASULI-II ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] |  |  | BILL/02912/2023-2024 | BP-2023-24-354 | 13/11/2023 | 13/11/2023 | WBSEDCL | 0.51 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GURIAMARI] WATER SUPPLY ASCHEME [ APPLICATION --2004479524, REFERENCE ID ----204122240, NIMPURA CCC, QUOTATION NO ---2004479524/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GURIAMARI ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ], |  |  | BILL/02913/2023-2024 | BP-2023-24-353 | 13/11/2023 | 13/11/2023 | WBSEDCL | 3.5 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ GERIASULI-I] WATER SUPPLY ASCHEME [ APPLICATION --2004479494, REFERENCE ID ----204122247, NIMPURA CCC, QUOTATION NO ---2004479494/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ GERIASULI-I] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] |  |  | BILL/02914/2023-2024 | BP-2023-24-350 | 10/11/2023 | 10/11/2023 | WBSEDCL | 4.75 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | QUOTATION FOR NEW POWER CONNECTION OF HARIATARA [ MULBANDH] WATER SUPPLY ASCHEME [ APPLICATION --2004479472, REFERENCE ID ----204122244, NIMPURA CCC, QUOTATION NO ---2004479472/QUOT/03 DATED 26/10/2023, SCHEME NAME --- HARIATARA [ MULBANDH ] . , SCHEME CODE ---SM/14483 , MB NO--3580 ] |  |  | BILL/02911/2023-2024 | BP-2023-24-347 | 10/11/2023 | 10/11/2023 | WBSEDCL | 0.51 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Construction of Pump House, Laying Rising main, Boundary wall, Laying distribution system pipe line, Accommodate FHTC (252 Nos.) including 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000043/2023-2024 | 1408/MD | 04/05/2023 | 22/05/2025 | R. CONSTRUCTION | 88.64 | 65.99 | 74.45 | 65
10 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (252 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000092/2023-2024 | 2468/MD | 14/07/2023 | 05/03/2025 | WATER LINK | 69.34 | 39.47 | 56.93 | 70
11 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000093/2023-2024 | 2469/MD | 14/07/2023 | 09/12/2025 | GOUTAM PARIA | 44.55 | 29.92 | 67.18 | 75
12 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (152 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000095/2023-2024 | 2470/MD | 14/07/2023 | 12/09/2023 | BUNBA CONSTRUCTION | 34.51 | 21.45 | 62.14 | 68
13 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (269 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000096/2023-2024 | 2471/MD | 14/07/2023 | 28/05/2026 | MIDNAPUR PIPE CONCERN | 80.7 | 57.58 | 71.34 | 70
14 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000097/2023-2024 | 2472/MD | 14/07/2023 | 12/09/2023 | DEBASISH DOGRA | 47.36 | 31.52 | 66.55 | 95
15 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Laying distribution system pipe line & Accommodate FHTC (152 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-V] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000171/2023-2024 | 2673/MD | 26/07/2023 | 09/09/2023 | AJIJUR RAHAMAN MALLICK | 26.72 | 14.01 | 52.42 | 80
16 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Construction of Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, FHTC (100 Nos.) under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000146/2023-2024 | 2638/MD | 24/07/2023 | 22/09/2023 | HYDRO TECH ASSOCIATES | 15.63 | 7.88 | 50.43 | 75
17 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Laying distribution pipe line with Rising Main, Switch Room (3750 X 2550) along with PVC water storage OHR having capacity 20 Cum & St. Ht. 8.50 Mtr. erected over roof of Switch Room by M.S. fabricated structure, Development H/W site FHTC (117 Nos.) & 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE3 Kharagpur Sub-division | ORD/000844/2023-2024 | 805/MD | 15/03/2024 | 14/05/2024 | AJIJUR RAHAMAN MALLICK | 42.9 | 34.92 | 81.38 | 92
18 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Construction of Pump House, Laying Rising main, Boundary wall, Laying distribution system pipe line, Accommodate FHTC (252 Nos.) including 2 yrs. O&M under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000011/2024-2025 | 1965/MD | 26/06/2024 | 22/04/2025 | DEBASISH DOGRA | 97.72 | 0 | 0 | 55
19 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Sinking of 2 Nos. Tube well under JJM with allied work for Hariatara PWSS (Zone-III) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000166/2023-2024 | 2669/MD | 26/07/2023 | 16/08/2023 | DEBASISH DOGRA | 12.01 | 10.95 | 91.19 | 100
20 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | QUOTATION MONEY FOR HARIATARA WATER SUPPLY SCHEME (PORADIHA), JJM WORKS, SCHEME CODE SM/14483, APPLICATION NO 2004576970, REFERENCE ID 204203221, NIMPURA CCC, WBSEDCL |  |  | BILL/03730/2023-2024 | BP-2023-24-701 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.26 | 0 | 0 | 0
21 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | QUOTATION MONEY FOR HARIATARA WATER SUPPLY SCHEME, ZONE-I, T W NO II, JJM WORKS, SCHEME CODE SM/14483, APPLICATION NO 2004576786, REFERENCE ID 204203220, NIMPURA CCC, WBSEDCL |  |  | BILL/04703/2023-2024 | BP-2023-24-917 | 28/03/2024 | 28/03/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
22 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, and III) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte.(Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002026/2022-2023 | 934/W/MMD | 28/03/2023 | 24/09/2023 | SUBHASIS ROY | 11.97 | 0 | 0 | 90
23 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Construction of RCC OHR (150 CuM), Pump House, Boundary wall & Accommodate FHTC (335 Nos.) under JJM with allied work for Hariatara PWSS (Zone-II) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000303/2024-2025 | 3399/MD | 25/11/2024 | 24/05/2025 | A K SIKDAR | 110.39 | 0 | 0 | 15
24 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Hariatara (Zone-I, II, & III) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14483 | New | Construction of RCC OHR (150 CuM), Pump House, Boundary wall & Accommodate FHTC (324 Nos.) under JJM with allied work for Hariatara PWSS (Zone-I) in Kharagpur-I block including supply of all labour & materials within Kharagpur Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000314/2024-2025 | 3479/MD | 26/11/2024 | 21/11/2025 | DEBASISH DOGRA | 109.07 | 0 | 0 | 20
Total | [13 empty] | 918.65 | 368 | 40.06