## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KUBIR CHAK PIPED WATER SUPPLY SCHEME | SM/14484 | New | Material Requisition To Resource Division |  |  | RTOR000050/2024-2025 | 3370/MD | 25/11/2024 | 25/11/2024 | Resource Division | 9.42 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KUBIR CHAK PIPED WATER SUPPLY SCHEME | SM/14484 | New | ELECTRIC QUOTATION BILL FOR TW NO-II of KUBIR CHAK PWSS. REF CONSUMER ID-204240650, APPLICATION NO-2004634372, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/04478/2023-2024 | BP-2023-24-848 | 14/03/2024 | 14/03/2024 | WBSEDCL | 4.34 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KUBIR CHAK PIPED WATER SUPPLY SCHEME | SM/14484 | New | ELECTRIC QUOTATION BILL FOR TW NO-I of KUBIR CHAK PWSS. REF CONSUMER ID-204266459, APPLICATION NO-2004670480, APPLICATION TYPE-NEW CONNECTION, NAME OF CCC-UPPERKUAI CCC, NAME OF BLOCK-KESHPUR |  |  | BILL/00290/2024-2025 | BP-2024-25-46 | 18/04/2024 | 18/04/2024 | WBSEDCL | 4.92 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KUBIR CHAK PIPED WATER SUPPLY SCHEME | SM/14484 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 07/01/2026 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KUBIR CHAK PIPED WATER SUPPLY SCHEME | SM/14484 | New | Laying of rising main & interconnection for Kubir Chak & its adjoining mouzas PWSS, Block ¿ Keshpur, District ¿ Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 400 Mtr.). | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000383/2024-2025 | 58/MD | 07/01/2025 | 21/02/2025 | MAHALAKSHMI ENTERPRISE | 5.68 | 0 | 0 | 100
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KUBIR CHAK PIPED WATER SUPPLY SCHEME | SM/14484 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUBIR CHAK PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001591/2022-2023 | 457/W/MMD | 20/03/2023 | 02/06/2025 | KAMAKSHYA ENTERPRISE | 22.77 | 0 | 0 | 25
Total | [13 empty] | 5779.43 | 0 | 0