## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | Material Requisition To Resource Division |  |  | RTOR000112/2022-2023 | 208/MD | 16/01/2023 | 16/01/2023 | Resource Division | 30.42 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | Material Requisition To Resource Division |  |  | RTOR000072/2024-2025 | 3422/MD | 25/11/2024 | 25/11/2024 | Resource Division | 11.76 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME,ZONE-II/I, T W - I ,[ RAMNAGAR ] JJM WORKS, SCHEME CODE SM/14492, KGP-I, APPLICATION NO 2004696766, REFERENCE ID 204284088, NIMPURA CCC, WBSEDCL |  |  | BILL/00635/2024-2025 | BP-2024-25-120 | 06/05/2024 | 06/05/2024 | WBSEDCL | 0.11 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | CERTIFIED THAT IT IS QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME (SANKARACHAK) , MINI, ZONE-I , JJM WORKS, SCHEME CODE SM/14492, , APPLICATION NO 2004582819, REFERENCE ID 204206253, NIMPURA CCC, WBSEDCL |  |  | BILL/03699/2023-2024 | BP-2023-24-702 | 16/02/2024 | 16/02/2024 | WBSEDCL | 0.12 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | QUOTATION MONEY FOR KASHIJORA, ZONE-II/I, T W NO II [ BENAPURUR CHAITA ] WATER SUPPLY SCHEME, JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004890141, REFERENCE ID 204393532, NIMPURA CCC, WBSEDCL |  |  | BILL/03033/2024-2025 | C112429713000 | 25/11/2024 | 25/11/2024 | WBSEDCL | 4.28 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | QUOTATION MONEY FOR KASHIJORA WATER SUPPLY SCHEME ( SANKARCHAK ), MINI, ZONE-I JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582819, REFERENCE ID 204206253, NIMPURA CCC, WBSEDCL |  |  | BILL/00595/2024-2025 |  | 24/04/2024 | 24/04/2024 | WBSEDCL | 0.12 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | KASHIJORA WATER SUPPLY SCHEME, ZONE I , T W NO 2 , JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582759, REFERENCE ID 204223621, NIMPURA CCC, WBSEDCL |  |  | BILL/04203/2023-2024 | BP-2023-24-771 | 05/03/2024 | 05/03/2024 | WBSEDCL | 3.29 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | KASHIJORA WATER SUPPLY SCHEME, ZONE I , T W NO 1 , JJM WORKS, SCHEME CODE SM/14492, APPLICATION NO 2004582753, REFERENCE ID 204224605, NIMPURA CCC, WBSEDCL |  |  | BILL/04189/2023-2024 | BP-2023-24-770 | 04/03/2024 | 04/03/2024 | WBSEDCL | 3.25 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Division | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | Sinking of Tube wells, Construction of 250 CuM Capacity R.C.C Over Head Reservoirs (Over Raft Foundation) including Sub-Soil investigation works with Laying distribution system, Pump Houses, Boundary walls & Providing Functional Household Tap Connection (5415 nos.) including Two years O&M for AMBA (ZONE-I, II & III) & KASHIJORA (ZONE-I & II) Pipe W/S Scheme within Kharagpur-I Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000091/2023-2024 | 2465/MD | 14/07/2023 | 07/05/2026 | GOBINDA MAITY | 1571.51 | 402.25 | 25.6 | 42
10 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | Supply and Installation of ( Dept. ) Submersible Pumping Machinery, Voltage Stabilizer ( Dept. ) , Chlorination System ( Dept. ) and Internal House Wiring and other allied works at Tube Well no 2 of Kashijora Mini Water Supply Scheme , Zone -II [ Block- Kharagpur-I ] under MMD, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000053/2024-2025 | 730/MMSD-I | 07/06/2024 | 07/06/2025 | PURUSHOTTAM ENTERPRISE | 2.86 | 1.46 | 51.27 | 87
11 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I and II) and its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. .(Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002027/2022-2023 | 935/W/MMD | 28/03/2023 | 13/09/2025 | RISHAV ENTERPRISE | 5.98 | 5.26 | 88.02 | 80
12 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001631/2022-2023 | 538/W/MMD | 20/03/2023 | 27/02/2025 | SOUMEN ELECTRIC | 34.15 | 23.62 | 69.16 | 55
13 | PASCHIM MEDINIPUR | Kharagpur-I | Midnapore Mechanical | Ground Based Pipe Water Supply Scheme for Kashijora (Zone-I & II) & its adjoining mouzas, Block - Kharagpur-I, Dist.- Paschim Medinipur. | SM/14492 | New | Supply and Installation of ( Dept. ) Submersible Pumping Machinery, Voltage Stabilizer ( Dept. ) , Chlorination System ( Dept. ) and Internal House Wiring and other allied works at Tube Well no 1 of Kashijora Mini Water Supply Scheme , Zone -II [ Block- Kharagpur-I ] under MMD, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000052/2024-2025 | 732/MMSD-I | 07/06/2024 | 21/04/2025 | M/S SREEJIT ENTERPRISE | 2.87 | 2.1 | 73.09 | 100
Total | [13 empty] | 1670.7 | 434.69 | 26.02