## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/14493 | New | Material Requisition To Resource Division |  |  | RTOR000117/2022-2023 | 1461/MD | 08/05/2023 | 08/05/2023 | Resource Division | 62.18 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/14493 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001575/2022-2023 | 459/W/MMD | 20/03/2023 | 16/09/2023 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 60
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/14493 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (1844 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Manibpur & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000129/2023-2024 | 2538/MD | 19/07/2023 | 14/02/2026 | SUJATA CONSTRUCTION | 435.01 | 0 | 0 | 25
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/14493 | New | Quotation for new power connection at Manibpur water supply scheme T/W - I |  |  | BILL/03564/2023-2024 | BP-2023-24-619 | 07/02/2024 | 07/02/2024 | WBSEDCL | 4.3 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | MANIBPUR & ITS ADJOINING MOUZAS PIPED WATER SUPPLY SCHEME. | SM/14493 | New | Quotation for new power connection at Manibpur PWSS , T/W - II , Application no - 2004582208 , Ref ID - 204206278 , Madpur CCC |  |  | BILL/03747/2023-2024 | BP-2023-24-708 | 16/02/2024 | 16/02/2024 | WBSEDCL | 4.14 | 0 | 0 | 0
Total | [13 empty] | 528.52 | 0 | 0