## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14506 | New | Electric Quotation bill for Tw No-I of Khasjangal water supply scheme. (ref Consumer ID-204109026) |  |  | BILL/02899/2023-2024 | BP-2023-24-330 | 03/11/2023 | 03/11/2023 | WBSEDCL | 2.83 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14506 | New | Electric Quotation bill for Tw no-II of Khasjangal water supply scheme.(Ref Consumer ID-204109024) |  |  | BILL/02900/2023-2024 | BP-2023-24-331 | 03/11/2023 | 03/11/2023 | WBSEDCL | 3.58 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14506 | New | Material Requisition To Resource Division |  |  | RTOR000058/2024-2025 | 3378/MD | 25/11/2024 | 25/11/2024 | Resource Division | 12.14 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14506 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) for GAMARIA, UTTAR PIASHALA, KHAS JANGAL, ELUNI, GOPAL BANDH, JHETA JAMBONI, KUBIR CHAK & KUSUMDAHARI Pipe Water Supply Scheme within Keshpur Block under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000183/2023-2024 | 2735/MD | 01/08/2023 | 07/01/2026 | M/S. S.S. ENTERPRISE | 5732.3 | 0 | 0 | 75
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14506 | New | Laying of rising main & interconnection for Khas Jangal & its adjoining mouzas PWSS, Block - Keshpur, District - Paschim Medinipur under Midnapore Division, PHE Dte. (Length = 420 Mtr.) | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000539/2024-2025 | 730/MD | 18/03/2025 | 02/05/2025 | MALLICK ENTERPRISE | 5.4 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KHAS JANGAL PIPED WATER SUPPLY SCHEME | SM/14506 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KHAS JANGAL PIPED WATER SUPPLY SCHEME under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001616/2022-2023 | 495/W/MMD | 20/03/2023 | 02/01/2026 | M/S MANABESH ROY | 22.91 | 0 | 0 | 25
Total | [13 empty] | 5779.16 | 0 | 0