## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 11/06/2023 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
2 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Material Requisition To Resource Division |  |  | RTOR000271/2023-2024 | 3983/MD | 06/10/2023 | 06/10/2023 | Resource Division | 54.29 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Electric quotation bill for Tw no-I of Piasala PWSS. (Ref ID- 204061141) |  |  | BILL/01764/2023-2024 | BP-2023-24-183 | 11/08/2023 | 11/08/2023 | WBSEDCL | 2.75 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Mechanical | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Electric quotation bill for Tw No-II of Piasala water supply scheme. (ref Id-204061139) |  |  | BILL/01765/2023-2024 | BP-2023-24-184 | 11/08/2023 | 11/08/2023 | WBSEDCL | 2.82 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (500 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-IV] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000017/2023-2024 | 1023/MD | 12/04/2023 | 11/06/2023 | ASHIM KUMAR DEY | 137.59 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Laying distribution pipe line & Accommodate FHTC (470 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VI] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000018/2023-2024 | 937/MD | 04/04/2023 | 14/03/2025 | J.K. BUILDERS | 82.89 | 0 | 0 | 100
7 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Sinking of tube well & Accommodate FHTC (200 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VIII] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000041/2023-2024 | 1385/MD | 02/05/2023 | 16/06/2023 | DEBJIT PATRA | 29.29 | 0 | 0 | 50
8 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Sinking of Tube well & Accommodate FHTC (200 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-I] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000016/2023-2024 | 936/MD | 04/04/2023 | 19/05/2023 | ANNAPURNA TUBEWELL WORKS | 29.28 | 0 | 0 | 100
9 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Laying distribution pipe line & Accommodate FHTC (307 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-VII] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000019/2023-2024 | 938/MD | 04/04/2023 | 03/06/2023 | GOUTAM RAY | 52.89 | 0 | 0 | 53
10 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | New Service connection charges. |  |  | BILL/01287/2023-2024 | 58/JMD | 08/02/2024 | 08/02/2024 | WBSEDCL | 4.38 | 0 | 0 | 0
11 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | New Service connection charges. |  |  | BILL/01288/2023-2024 | 59/JMD | 08/02/2024 | 08/02/2024 | WBSEDCL | 5.04 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Garbeta-II | Central Drilling | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
13 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Construction Pump House, Boundary wall, Soil investigation, Construction of 450 cum OHR (Intze type with solid raft) & Accommodate FHTC (500 nos.) under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-II] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000035/2024-2025 | 2144/MD | 11/07/2024 | 06/07/2025 | KISHORE GHOSH | 179.06 | 0 | 0 | 5
14 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Laying distribution pipe line, Rising main, Pump House, Boundary wall, Accommodate FHTC (450 nos.) & 2 years operation & maintenance under JJM with allied work for Piasala & its adjoining mouzas PWSS in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-III] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000036/2024-2025 | 2145/MD | 11/07/2024 | 03/07/2025 | KISHORE GHOSH | 130.76 | 0 | 0 | 30
15 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | PIASALA AND ADJOINING MOUJAS PWSS | SM/14628 | New | Laying of additional distribution pipeline for Piasala & its adjoining mouzas PWSS, Block - Garhbeta-II, District - Paschim Medinipur under Midnapore Division, PHE Dte. | AE Sadar Sub-division |  | ORD/000518/2024-2025 | 699/MD | 12/03/2025 | 11/05/2025 | SAFTI PRIVATE LIMITED | 11.63 | 0 | 0 | 0
Total | [13 empty] | 22172.37 | 0 | 0