## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | BHATMARA AND ADJOINING MOUJAS PWSS | SM/14644 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 11/06/2023 | JADAVPUR UNIVERSITY | 109.92 | 4.78 | 4.35 | 35
2 | PASCHIM MEDINIPUR | Garbeta-I | Central Drilling | BHATMARA AND ADJOINING MOUJAS PWSS | SM/14644 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
3 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | BHATMARA AND ADJOINING MOUJAS PWSS | SM/14644 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,23,486 Nos.) for 89 Nos. PWSS within GARBETA-I, GARBETA-III, SALBANI & GARBETA-II Block Pipe Water Supply Scheme under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II),JE RWS Sadar Sub-Division(Garbeta-III),JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000282/2023-2024 | 5091/MD | 30/10/2023 | 19/10/2026 | RMN INFRASTRUCTURES LIMITED | 34739.93 | 31.57 | 0.09 | 40
4 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | BHATMARA AND ADJOINING MOUJAS PWSS | SM/14644 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 1192/MD | 26/04/2023 | 26/04/2023 | Resource Division | 13.69 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Garbeta-I | Central Drilling | BHATMARA AND ADJOINING MOUJAS PWSS | SM/14644 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). |  |  | ORD/000002/2024-2025 | 188/CDD | 17/05/2024 | 17/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 700.39 | 9.95 | 1.42 | 15
6 | PASCHIM MEDINIPUR | Garbeta-I | Central Drilling | BHATMARA AND ADJOINING MOUJAS PWSS | SM/14644 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 0 | 0 | 10
7 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | BHATMARA AND ADJOINING MOUJAS PWSS | SM/14644 | New | New Service Connection Charges for Bhatmara T/W-I PWSS |  |  | BILL/00370/2025-2026 |  | 08/05/2025 | 08/05/2025 | WBSEDCL | 3.87 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | BHATMARA AND ADJOINING MOUJAS PWSS | SM/14644 | New | NEW SERVICE CONNECTION CHARGES AT Bhatmara-II |  |  | BILL/01442/2025-2026 |  | 03/11/2025 | 03/11/2025 | WBSEDCL | 10.69 | 0 | 0 | 0
Total | [13 empty] | 57376.94 | 46.3 | 0.08