## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | GHRITAGRAM AND ADJOINING MOUJAS PWSS | SM/14648 | New | Material Requisition To Resource Division |  |  | RTOR000132/2023-2024 | 1325/MD | 28/04/2023 | 28/04/2023 | Resource Division | 18.04 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | GHRITAGRAM AND ADJOINING MOUJAS PWSS | SM/14648 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments at Newly sunk Tube well at GRITHAGRAM Water supply scheme, Keshiary block, District - Paschim Medinipur under Midnapore Mechanical Division P.H.E. Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/002720/2023-2024 | 1065/W/MMD | 14/03/2024 | 09/03/2025 | M/S EMMESS | 12.39 | 7.44 | 60.05 | 30
3 | PASCHIM MEDINIPUR | Keshiary | Central Drilling | GHRITAGRAM AND ADJOINING MOUJAS PWSS | SM/14648 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 220 Mtrs. Depth) by utilizing Departmental Machineries for Ghritagram W/S Scheme (TW-I & II), Keshiary Block under Paschim Medinipur District, Central Drilling Division, P.H.E. Dte. | Driller In Charge | Junior Engineer | ORD/000116/2023-2024 | 1437/CDD | 26/09/2023 | 26/10/2023 | M/S B.P.TRADING CORPORATION | 25.32 | 20.3 | 80.17 | 100
4 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | GHRITAGRAM AND ADJOINING MOUJAS PWSS | SM/14648 | New | Material Requisition To Resource Division |  |  | RTOR000073/2024-2025 | 3423/MD | 25/11/2024 | 25/11/2024 | Resource Division | 14.32 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | GHRITAGRAM AND ADJOINING MOUJAS PWSS | SM/14648 | New | Electric quotation bill for Tw No-I of Ghritagram PWSS. Ref Consumer ID-204175253) |  |  | BILL/03332/2023-2024 | BP-2023-24-552 | 17/01/2024 | 17/01/2024 | WBSEDCL | 3.53 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | GHRITAGRAM AND ADJOINING MOUJAS PWSS | SM/14648 | New | Electric quotation bill for Tw No-II of Ghritagram PWSS .(Ref Consumer ID-204175255) |  |  | BILL/03333/2023-2024 | BP-2023-24-553 | 16/01/2024 | 16/01/2024 | WBSEDCL | 3.05 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshiary | Midnapore Division | GHRITAGRAM AND ADJOINING MOUJAS PWSS | SM/14648 | New | Construction of Different Capacity R.C.C. Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with Laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (72023 Nos.) for 41 Nos. PWSS within DANTAN-I, DANTANII & KESHIARY Block Pipe Water Supply Scheme under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Midnapur Sub-Division(Dantan-II),JE RWS Kharagpur Sub-Division( Keshiary),JE RWS Midnapur Sub-Division( Dantan-I),JE2 Kharagpur Sub Division | ORD/000277/2023-2024 | 5056/MD | 26/10/2023 | 26/03/2026 | ENGINEERING PROJECTS (INDIA) LIMITED | 18003.47 | 194.69 | 1.08 | 30
8 | PASCHIM MEDINIPUR | Keshiary | Midnapore Mechanical | GHRITAGRAM AND ADJOINING MOUJAS PWSS | SM/14648 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for GHRITAGRAM AND ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001433/2023-2024 | 3087/W/MMD | 29/11/2023 | 22/05/2025 | PADMA ENGINEERING CO. | 10.99 | 7.56 | 68.79 | 25
Total | [13 empty] | 18091.1 | 229.99 | 1.27