## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Gopmahal urf Monaharpur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000659/2022-2023 | 1765/MD | 24/08/2022 | 13/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.05 | 3.15 | 77.65 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | Material Requisition To Resource Division |  |  | RTOR000287/2023-2024 | 4059/MD | 12/10/2023 | 12/10/2023 | Resource Division | 23.42 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,690 Nos.) under JJM with allied work for Gopmahal PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000637/2022-2023 | 555/MD | 22/02/2023 | 21/08/2023 | ASHIM KUMAR DEY | 353.2 | 65.31 | 18.49 | 15
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | Material Requisition To Resource Division |  |  | RTOR000033/2024-2025 | 3360/MD | 25/11/2024 | 25/11/2024 | Resource Division | 4.77 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | GOPMAHAL WATER SUPPLY SCHEME, PH - I, BLOCK - GHATAL , SCHEME - SM/14651, REF. ID - 204135807, GHATAL CCC, |  |  | BILL/03009/2023-2024 | BP-2023-24-391 | 02/12/2023 | 02/12/2023 | WBSEDCL | 2.91 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | QUOTATION MONEY FOR SHIFTING OF HT LINE ALONG WITH DTR OF GOPMAHAL URF MONAHARPUR WATER SUPPLY SCHEME, T W - I , JJM WORKS, SCHEME CODE SM/14651, APPLICATION NO 100000109467, REFERENCE ID 860301697, GHATAL CCC, WBSEDCL |  |  | BILL/01333/2024-2025 | BP-2024-25-357 | 01/07/2024 | 01/07/2024 | WBSEDCL | 2.02 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001577/2022-2023 | 461/W/MMD | 20/03/2023 | 16/09/2023 | M/S B.M. ELECTRICAL | 22.89 | 14.77 | 64.53 | 40
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 17/02/2024 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Gopmahal urf Monaharpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14651 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
Total | [13 empty] | 419.85 | 83.23 | 19.82