## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | JHARBHANGA AND ADJOINING MOUJAS PWSS | SM/14652 | New | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 1303/MD | 28/04/2023 | 28/04/2023 | Resource Division | 32.22 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | JHARBHANGA AND ADJOINING MOUJAS PWSS | SM/14652 | New | New service connection charges for Jharbhanga, t/w-II w/s scheme |  |  | BILL/01320/2023-2024 | 88/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.4 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | JHARBHANGA AND ADJOINING MOUJAS PWSS | SM/14652 | New | New service connection charges for Jharbhanga, t/w-I w/s scheme |  |  | BILL/01308/2023-2024 | 79/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.39 | 0 | 0 | 0
Total | [13 empty] | 39 | 0 | 0