## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KASHBA AND ITS ADJOINING MOUZAS PWSS | SM/14653 | New | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 195/MD | 16/01/2023 | 16/01/2023 | Resource Division | 15.49 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KASHBA AND ITS ADJOINING MOUZAS PWSS | SM/14653 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KASHBA AND ITS ADJOINING MOUZAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000147/2023-2024 | 1378/W/MMD | 30/05/2023 | 26/11/2023 | THE BUSINESS ENGINEERING INDIA | 11.98 | 0 | 0 | 15
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KASHBA AND ITS ADJOINING MOUZAS PWSS | SM/14653 | New | Material Requisition To Resource Division |  |  | RTOR000074/2024-2025 | 3424/MD | 25/11/2024 | 25/11/2024 | Resource Division | 2.83 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KASHBA AND ITS ADJOINING MOUZAS PWSS | SM/14653 | New | Quotation for new power connection at kasba water supply scheme T/W - I |  |  | BILL/03583/2023-2024 | BP-2023-24-640 | 08/02/2024 | 08/02/2024 | WBSEDCL | 0.51 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KASHBA AND ITS ADJOINING MOUZAS PWSS | SM/14653 | New | Quotation for new power connection at Kasba water supply scheme T/W - I |  |  | BILL/03557/2023-2024 | BP-2023-24-641 | 08/02/2024 | 08/02/2024 | WBSEDCL | 4.6 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KASHBA AND ITS ADJOINING MOUZAS PWSS | SM/14653 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 100 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (459 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Kashba & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000066/2023-2024 | 2147/MD | 08/06/2023 | 24/02/2026 | A.J. ENTERPRISE | 205.4 | 0 | 0 | 65
Total | [13 empty] | 240.8 | 0 | 0