## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Material Requisition To Resource Division |  |  | RTOR000105/2022-2023 | 212/MD | 16/01/2023 | 16/01/2023 | Resource Division | 42.05 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Material Requisition To Resource Division |  |  | RTOR000075/2024-2025 | 3425/MD | 25/11/2024 | 25/11/2024 | Resource Division | 13.45 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Quotation for new power connection at Kukrada PWSS TW - II with in Narayangarh Block Application No - 2005005228 Ref ID - 204471132 |  |  | BILL/03674/2024-2025 |  | 18/12/2024 | 18/12/2024 | WBSEDCL | 6.21 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUKRADA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001623/2022-2023 | 500/W/MMD | 20/03/2023 | 16/06/2025 | PADMA ENGINEERING CO. | 23 | 0 | 0 | 80
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 Cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,184 nos.) under JJM with allied work including 02 (Two) Years Operation & Maintenance for Kukrada & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000459/2023-2024 | 5283/MD | 23/11/2023 | 12/11/2025 | CREATION CONSTRUCTION | 530.64 | 123.28 | 23.23 | 60
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KUKRADA AND ITS ADJOINING MOUZAS PWSS | SM/14654 | New | Route survey & way leave permission along & across of National Highway in Kukrada PWSS under Kharagpur Sub-Division of Midnapore Division, PHE Dte. | AE Kharagpur Sub-division |  | ORD/000488/2024-2025 | 522/MD | 19/02/2025 | 12/03/2025 | PIONEER SURVEYORS | 9.44 | 0 | 0 | 0
Total | [13 empty] | 624.8 | 123.28 | 19.73