## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KULDIHA AND ITS ADJOINING MOUZAS PWSS | SM/14655 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KULDIHA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001576/2022-2023 | 460/W/MMD | 20/03/2023 | 16/09/2023 | BALAJI CONSTRUCTION | 22.89 | 0 | 0 | 50
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KULDIHA AND ITS ADJOINING MOUZAS PWSS | SM/14655 | New | Sinking of 2 (Two) Nos. Tube well for Kuldiha & its adjoining mouzas PWSS in Kharagpur-II block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division(KGP-II),JE3 Kharagpur Sub-division | ORD/000137/2023-2024 | 2621/MD | 24/07/2023 | 07/04/2025 | R. CONSTRUCTION | 16.52 | 0 | 0 | 50
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KULDIHA AND ITS ADJOINING MOUZAS PWSS | SM/14655 | New | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 1362/MD | 02/05/2023 | 02/05/2023 | Resource Division | 29.38 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | KULDIHA AND ITS ADJOINING MOUZAS PWSS | SM/14655 | New | Laying distribution pipe line, Pump House, Boundary Wall, soil investigation, 250 Cum OHR ((Intze type with solid raft ) & Accommodate FHTC (2,237 nos.) under JJM with allied work for Kuldiha & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials including 02(Two) Years Operation & Maintanance under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000010/2024-2025 | 1964/MD | 26/06/2024 | 21/06/2025 | ANIRUDDHA BAG | 517.34 | 2.7 | 0.52 | 25
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KULDIHA AND ITS ADJOINING MOUZAS PWSS | SM/14655 | New | Construction of materials godown alongwith internal electrification and illumination and other works at the campus of the office of Assistant Engineer under MMSD-I, PHE Dte., Dist.- Paschim Medinipur. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002724/2023-2024 | 1069/W/MMD | 14/03/2024 | 10/09/2024 | SWAPAN BANERJEE | 10.42 | 0 | 0 | 100
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KULDIHA AND ITS ADJOINING MOUZAS PWSS | SM/14655 | New | Quotation for new power connection at Kuldiha PWSS tw - II within Khargpur - II Block , Application No - 2005012222 , Ref ID - 204476964 |  |  | BILL/03685/2024-2025 | C012552594276 | 31/01/2025 | 31/01/2025 | WBSEDCL | 3.18 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | KULDIHA AND ITS ADJOINING MOUZAS PWSS | SM/14655 | New | Quotation for new power connection at Kuldiha PWSS tw - I within Khargpur - II Block , Application No - 2005012216 , Ref ID - 204476963 |  |  | BILL/03689/2024-2025 | C012552590212 | 31/01/2025 | 31/01/2025 | WBSEDCL | 3.15 | 0 | 0 | 0
Total | [13 empty] | 602.87 | 2.7 | 0.45