## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14656 | New | Preparation & Submission of 2 (Two) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Kuran & its adjoining Mouzas PWSS AND (2) Kushman & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division |  | ORD/000660/2022-2023 | 1766/MD | 24/08/2022 | 23/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.92 | 3.46 | 50 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14656 | New | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 64/MD | 09/01/2023 | 09/01/2023 | Resource Division | 17.03 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14656 | New | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | 3362/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.15 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14656 | New | QUOTATION MONEY FOR KUSHMAN WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/14656, APPLICATION NO 2004816276, REFERENCE ID 204354169, BIRSHINGHA CCC, WBSEDCL |  |  | BILL/01731/2024-2025 | C072445025889 | 30/07/2024 | 30/07/2024 | WBSEDCL | 5.09 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14656 | New | QUOTATION MONEY FOR KUSHMAN WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14656, APPLICATION NO 2004816294, REFERENCE ID 204354171, BIRSHINGHA CCC, WBSEDCL |  |  | BILL/01732/2024-2025 | C072445022964 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.85 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Kushman & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14656 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 250 cum OHR (Intze type with pile foundation) & Accommodate FHTC (1,647 nos.) under JJM with allied work for Kushman PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000036/2023-2024 | 1338/MD | 28/04/2023 | 28/09/2025 | M/S. D.K.H.CONSTRUCTION | 444.51 | 89.22 | 20.07 | 8
Total | [13 empty] | 487.53 | 92.68 | 19.01