## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | BAGDOBA AND ADJOINING MOUJAS PWSS | SM/14690 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 11/06/2023 | JADAVPUR UNIVERSITY | 109.92 | 4.78 | 4.35 | 35
2 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Mechanical | BAGDOBA AND ADJOINING MOUJAS PWSS | SM/14690 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for BAGDOBA AND ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. (Part-II) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001960/2022-2023 | 872/W/MMD | 27/03/2023 | 23/09/2023 | SUJOY RANJAN BHOWMICK | 5.99 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | BAGDOBA AND ADJOINING MOUJAS PWSS | SM/14690 | New | Material Requisition To Resource Division |  |  | RTOR000052/2023-2024 | 1191/MD | 26/04/2023 | 26/04/2023 | Resource Division | 20.91 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | BAGDOBA AND ADJOINING MOUJAS PWSS | SM/14690 | New | NEW SERVICE CONNECTION CHARGES AT BAGDOBA-I WATER SUPPLY SCHEME |  |  | BILL/00648/2024-2025 | 261/JMD | 23/07/2024 | 23/07/2024 | WBSEDCL | 4.53 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | BAGDOBA AND ADJOINING MOUJAS PWSS | SM/14690 | New | Route survey & way leave permission along & across of National Highway in Bagdoba PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE1 Sadar Sub-division | ORD/000463/2024-2025 | 378/MD | 31/01/2025 | 21/02/2025 | DONA ASSOCIATES | 9.39 | 0 | 0 | 0
Total | [13 empty] | 150.74 | 4.78 | 3.17