## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Tap Connection for Rejuvenation of existing Kolanda PWSS within Sabang Block under Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000435/2021-2022 | 1668/MD | 28/09/2021 | 08/10/2021 | RISHAN ENGINEERING CONSULTANCY | 2.11 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR |  | Midnapore Division | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Restoration of pipe line damaged due to construction of roads (Koptipur, Rautarabari, Bangaldari, Hijaltol Batitaki, Batuabazar etc.) & excess length of pipe in connection with FHTC work at Kolanda W/S Scheme at Sabang Block under Kharagpur Sub-Division within Midnapore Division, P.H.E. Dte. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division( Sabang) | ORD/000613/2022-2023 | 439/MD | 10/02/2023 | 27/03/2023 | M/S. A.R. ENTERPRISE. | 68.31 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002243/2022-2023 | 186/MMSD-I | 27/02/2023 | 30/08/2023 | M/S BIKASH DE | 0.9 | 0 | 0 | 25
4 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002284/2022-2023 | 187/MMSD-I | 27/02/2023 | 30/08/2023 | SUBHASIS ROY | 0.9 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Electric quotation for Kolanda PWSS Tube Well-III WS Scheme (Ref. ID 203935156) |  |  | BILL/00415/2022-2023 | BP-2023-24-24 | 04/05/2023 | 04/05/2023 | WBSEDCL | 1.78 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Service connection charges of WBSEDCL at TW-IV (Additional) of Kolanda Water Supply Scheme (Ref. ID - 203935153) |  |  | BILL/00407/2022-2023 |  | 22/03/2023 | 22/03/2023 | WBSEDCL | 0.46 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Service connection charges of WBSEDCL at TW-III (Additional) of Kolanda Water Supply Scheme (Ref. ID - 203935156) |  |  | BILL/00406/2022-2023 |  | 22/03/2023 | 22/03/2023 | WBSEDCL | 1.78 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Electric quotation for Kolanda PWSS Tube Well-IV WS Scheme (Ref. ID 203935153) |  |  | BILL/00416/2022-2023 |  | 25/03/2023 | 25/03/2023 | WBSEDCL | 0.46 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | SUPPLY AND DELIVERY OF FUEL FOR INSPECTION VEHICAL FOR INSPECTION OF JJM WORK AT OFFICE OF THE ASSISTANT ENGINEER MMSD1 | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002279/2022-2023 | 186./MMSD-I | 27/02/2023 | 30/08/2023 | M/S BIKASH DE | 3 | 0 | 0 | 100
10 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Installation of Dept. Submersible Pump motor set and with other acessories and other allied works at Tubewell no 3 ( newly sunk ) of Kolanda Water Supply Scheme [ Block Sabong ] under MMD, PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002418/2023-2024 | 41/MMSD-I | 16/01/2024 | 23/01/2024 | SHOVAN KUMAR DAS | 0.3 | 0 | 0 | 100
11 | PASCHIM MEDINIPUR |  | Midnapore Mechanical | Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte. | SM/14720 | Augmentation | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Rejuvenation of Ground Water Based Piped Water Supply Scheme for Kolanda (Part) to Accommodate FHTC under Jal Sapno Mission under Sabang Block in Paschim Medinipur district under Midnapore Division, PHE Dte.under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/000172/2023-2024 | 1426/W/MMD | 05/06/2023 | 01/04/2025 | A.M.S. ENTERPRISE | 10.77 | 0 | 0 | 100
Total | [13 empty] | 90.8 | 0 | 0