## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-I | Midnapore Division | PACHADAHARA & ADJOINING MOUJAS PWSS | SM/14732 | New | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 1178/MD | 26/04/2023 | 26/04/2023 | Resource Division | 26.89 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-I | Jhargram Mechanical Division | PACHADAHARA & ADJOINING MOUJAS PWSS | SM/14732 | New | NEW SERVICE CONNECTION CHARGES AT POCHADOHARA TW-I WATER SUPPLY SCHEME |  |  | BILL/00568/2024-2025 | 247/JMD | 10/07/2024 | 10/07/2024 | WBSEDCL | 7.16 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-I | Central Drilling | PACHADAHARA & ADJOINING MOUJAS PWSS | SM/14732 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21373.81 | 0 | 0