## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS | SM/14939 | New | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 1143/MD | 25/04/2023 | 25/04/2023 | Resource Division | 16.01 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS | SM/14939 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KUMARSANDA AND IT'S ADJOINING MOUJAS PWSSunder JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/000080/2023-2024 | 1276/W/MMD | 04/05/2023 | 31/10/2023 | MENAKA ENTERPRISE | 22.54 | 20.89 | 92.68 | 90
3 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS | SM/14939 | New | Electric quotation bill for kumarsanda pwss at pump house NO-I (Ref Id-204159129) |  |  | BILL/03183/2023-2024 | BP-2023-24-458 | 21/12/2023 | 21/12/2023 | WBSEDCL | 5.97 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS | SM/14939 | New | Electric quotation bill for KUMARSANDA pwss at TW-II (Ref Id-204158498) |  |  | BILL/03242/2023-2024 | BP-2023-24-491 | 29/12/2023 | 29/12/2023 | WBSEDCL | 3.17 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Division | KUMARSANDA AND IT'S ADJOINING MOUJAS PWSS | SM/14939 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation works with laying rising main, distribution system , Sinking of Tube Well , Pump House , Boundary Wall, & Providing Functional Household Tap Connection (6348 Nos) including 2 years operation & maintenance For Chak Sulpan, Katai, Khanamohan, Khamra and Kumarsanda Pipe water supply Scheme within Debra Block Under Kharagpur Sub Division of Midnapore Division PHE Dte. Under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE1 Kharagpur Sub-division | ORD/000064/2023-2024 | 2145/MD | 08/06/2023 | 01/10/2025 | GOBINDA MAITY | 1960.6 | 203.6 | 10.38 | 65
Total | [13 empty] | 2008.29 | 224.49 | 11.18