## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS | SM/14940 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001942/2022-2023 | 827/W/MMD | 24/03/2023 | 20/09/2023 | ORIENTAL ENGINEERING CO. | 22.65 | 10.5 | 46.36 | 45
2 | PASCHIM MEDINIPUR | Debra | Midnapore Division | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS | SM/14940 | New | Construction of 150 Cum, 200 Cum & 250 Cum Capacity R.C.C Over Head Reservoir Over (Intze type with solid raft) works with Laying of Rising Main, Distribution system, Sinking of Tube Well, Pump House & Providing Functional Household Tap Connection (5061 Nos.) including 2 years Operation & Maintenance for Loyada, Madhabpur, Patna and Radhamohanpur-II Pipe Water Supply Scheme within Debra block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,AE/RWS Midnapore Sub Division | JE3 Kharagpur Sub-division | ORD/000208/2023-2024 | 2824/MD | 07/08/2023 | 30/07/2025 | MADE AND TRADE CO. | 1346.28 | 168.46 | 12.51 | 75
3 | PASCHIM MEDINIPUR | Debra | Midnapore Division | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS | SM/14940 | New | Material Requisition To Resource Division |  |  | RTOR000227/2023-2024 | 1510/MD | 12/05/2023 | 12/05/2023 | Resource Division | 22.87 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS | SM/14940 | New | Electrict quotation bill for TW-I of Radhamohanpur pwss (Ref Consumar ID-204439150),Application No-2004955822,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra |  |  | BILL/03035/2024-2025 | C112429737180 | 25/11/2024 | 25/11/2024 | WBSEDCL | 3.57 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS | SM/14940 | New | Electrict quotation bill for TW-II of Radhamohanpur pwss (Ref Consumar ID-204210515),Application No-2004585811,Application Type-New Connection,Name of ccc-Balichak ccc, block-Debra |  |  | BILL/03735/2023-2024 | BP-2023-24-704 | 16/02/2024 | 16/02/2024 | WBSEDCL | 5.95 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Debra | Midnapore Mechanical | RADHAMOHANPUR-II AND ITS ADJOINING MOUJAS PWSS | SM/14940 | New | Additional Electrict quotation bill for TW-II of Radhamohanpur pwss (Ref Consumar ID-860303412),Application No-100000110832,Application Type-New Connection,Name of ccc-Mohanpur ccc, block-Mohanpur |  |  | BILL/01364/2024-2025 | BP-2024-25-378 | 08/07/2024 | 08/07/2024 | WBSEDCL | 0.43 | 0 | 0 | 0
Total | [13 empty] | 1401.74 | 178.96 | 12.77