## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | SM/14941 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation at 3 Nos. of locations adjacent to the Bara Mahanpur of Narayangarh block in Paschim Medinipur district under Midnapore Division, PHE Dte. | AE/RWS Midnapore Sub Division |  | ORD/000734/2022-2023 | 708/MD | 06/03/2023 | 27/03/2023 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | SM/14941 | New | Material Requisition To Resource Division |  |  | RTOR000226/2023-2024 | 1484 | 10/05/2023 | 10/05/2023 | Resource Division | 24.73 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | SM/14941 | New | Quotation for new power connection at Bara Mohanpur PWSS T/W- I ,Narayangarh Block , Application no- 2004641957 , ref. Id - 404244873 |  |  | BILL/00700/2024-2025 | BP-2024-25-153 | 09/05/2024 | 09/05/2024 | WBSEDCL | 5.26 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | SM/14941 | New | Quotation for new power connection at Baramohanpur PWSS T/W - II under Narayangarh Block , Application no - 2004852851 , Ref No - 204373751. |  |  | BILL/02113/2024-2025 | C092402013162 | 04/09/2024 | 04/09/2024 | WBSEDCL | 4.02 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | SM/14941 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 15 | 0.07 | 11
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | SM/14941 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including sub soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (33,066 Nos.) For KASBA NARAYANGARH, KHURSI, NAHARPUR, NARMA, PAKURSENI, ASTI, BARA MAHANPUR, GOBINDAPUR BRAHMAN SASAN, JAMUNA, RERIPUR, TUTRANGA, SHUJANAGAR & GOKULPUR Pipe water supply Scheme within NARAYANGARH Block including 02 (Two) Years Operation & Maintenance Under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE1 Kharagpur Sub-division | ORD/000290/2023-2024 | 5049/MD | 25/10/2023 | 13/12/2025 | SWACH ENVIRONMENT PRIVATE LIMITED | 8498.31 | 93.19 | 1.1 | 41
7 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BARA MAHANPUR AND ADJOINING MOUJAS PWSS | SM/14941 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
Total | [13 empty] | 29893.04 | 108.19 | 0.36