## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 11/06/2023 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
2 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Material Requisition To Resource Division |  |  | RTOR000263/2023-2024 | 2039/MD | 18/05/2023 | 18/05/2023 | Resource Division | 27.2 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Accommodate FHTC (218 Nos.) & Construction of Boundary wall under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000144/2023-2024 | 2628/MD | 24/07/2023 | 07/09/2023 | M/S. BLUE BIRD | 31.54 | 0 | 0 | 25
4 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Laying distribution pipe line & Accommodate FHTC (400 Nos.) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000173/2023-2024 | 2675/MD | 26/07/2023 | 09/09/2023 | EVEREST CONSULTANT SERVICES | 66.12 | 0 | 0 | 80
5 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Sinking of Tube well, Laying distribution pipe line, Boundary wall, Pump House alongwith 20 CuM OHR (Zone-2) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme with Standalone in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-A] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000145/2023-2024 | 2636/MD | 24/07/2023 | 22/09/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.73 | 0 | 0 | 15
6 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Sinking of 2 (Two) Nos. Tube well for Amlasuli & its adjoining mouzas (Zone-I) PWSS in Garhbeta-II block including supply of all labour & materials under Midnapore Sadar Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000116/2023-2024 | 2517/MD | 18/07/2023 | 17/08/2023 | GARHBETA-1 UNEMPLOYED YOUTH ENGINEERS CO-OPERATIVE SOCIETY LTD. | 17.57 | 0 | 0 | 30
7 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | New service connection |  |  | BILL/01300/2023-2024 | 71/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 3.5 | 0 | 0 | 0
8 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | New service connection |  |  | BILL/01299/2023-2024 | 70/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.59 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Improvement of approach road of Bhansra PWSS Head Work Site under Kashiery Block within Midnapore Division P.H.E. Dte. | AE Kharagpur Sub-division |  | ORD/000384/2024-2025 | 10101/MD | 20/11/2024 | 20/12/2024 | K & KABERI ENTERPRISE (PROP. GOUTAM MAITY) | 0 | 0 | NAN | 0
10 | PASCHIM MEDINIPUR | Garbeta-II | Central Drilling | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
11 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Construction of 250 CuM OHR (Intze type with Solid raft) (Zone-1) & Accommodate FHTC (500 Nos.) under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000418/2024-2025 | 199/MD | 17/01/2025 | 12/01/2026 | DIPAK KUMAR BAKLY | 111.02 | 0 | 0 | 0
12 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | AMLASULI AND ADJOINING MOUJAS PWSS | SM/14989 | New | Laying of Rising main, Laying distribution pipe line, Pump House, Boundary wall & Accommodate FHTC (500 Nos.) including 2 years operation & maintenance under JJM with allied work for Amlasuli & its adjoining mouzas W/S Scheme in Garbeta-II block including supply of all labour & materials within Midnapore Sadar Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000421/2024-2025 | 200/MD | 17/01/2025 | 13/11/2025 | DIPAK KUMAR BAKLY | 117.81 | 0 | 0 | 0
Total | [13 empty] | 21867.76 | 0 | 0