## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Salbani | Central Drilling | BENACHAPRA AND ADJOINING MOUJAS PWSS | SM/14992 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 12.11 | 0.06 | 11
2 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENACHAPRA AND ADJOINING MOUJAS PWSS | SM/14992 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (1,23,486 Nos.) for 89 Nos. PWSS within GARBETA-I, GARBETA-III, SALBANI & GARBETA-II Block Pipe Water Supply Scheme under Midnapore Sadar Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II),JE RWS Sadar Sub-Division(Garbeta-III),JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000282/2023-2024 | 5091/MD | 30/10/2023 | 19/10/2026 | RMN INFRASTRUCTURES LIMITED | 34739.93 | 82.18 | 0.24 | 40
3 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENACHAPRA AND ADJOINING MOUJAS PWSS | SM/14992 | New | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 1258/MD | 28/04/2023 | 28/04/2023 | Resource Division | 26.15 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BENACHAPRA AND ADJOINING MOUJAS PWSS | SM/14992 | New | New service connection charges for Benachapra pwss, t/w no. II |  |  | BILL/00072/2024-2025 | 46/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.44 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Salbani | Jhargram Mechanical Division | BENACHAPRA AND ADJOINING MOUJAS PWSS | SM/14992 | New | New service connection charges for Benachapra pwss, t/w no.I |  |  | BILL/01370/2023-2024 | 33/JMD | 11/03/2024 | 11/03/2024 | WBSEDCL | 5.66 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Salbani | Midnapore Division | BENACHAPRA AND ADJOINING MOUJAS PWSS | SM/14992 | New | Route survey & way leave permission along & across of National Highway in Benachapra PWSS under Midnapore Sadar Sub-Division of Midnapore Division, PHE Dte. | AE Sadar Sub-division |  | ORD/000457/2024-2025 | 374/MD | 31/01/2025 | 21/02/2025 | DONA ASSOCIATES | 11.64 | 0 | 0 | 0
Total | [13 empty] | 56126.58 | 94.29 | 0.17