## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | BENADIHA AND ADJOINING MOUJAS PWSS | SM/14993 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 20.05 | 0.09 | 11
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BENADIHA AND ADJOINING MOUJAS PWSS | SM/14993 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7130 Nos) including 2 years Operation & Maintenance for Kashipur, Benadiha and Markunda Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000126/2023-2024 | 2524/MD | 18/07/2023 | 04/11/2025 | NABA KUMAR BHUNIA | 1870.43 | 410.46 | 21.94 | 82
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BENADIHA AND ADJOINING MOUJAS PWSS | SM/14993 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BENADIHA AND ADJOINING MOUJAS PWSS | SM/14993 | New | Laying additional quantity of distribution pipeline for providing FHTC at Kashipur, Benadiha & Markunda PWSS under Narayangarh block within Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000180/2024-2025 | 3165/MD | 05/10/2024 | 17/06/2025 | NABA KUMAR BHUNIA | 78.57 | 0 | 0 | 50
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | BENADIHA AND ADJOINING MOUJAS PWSS | SM/14993 | New | Material Requisition To Resource Division |  |  | RTOR000118/2024-2025 | 3454/MD | 25/11/2024 | 25/11/2024 | Resource Division | 19.82 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BENADIHA AND ADJOINING MOUJAS PWSS | SM/14993 | New | Quotation for new power connection at Benadiha water supply scheme T/W no I |  |  | BILL/03287/2023-2024 | BP-2023-24-500 | 05/01/2024 | 05/01/2024 | WBSEDCL | 4.63 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | BENADIHA AND ADJOINING MOUJAS PWSS | SM/14993 | New | Quotation for New power connection at Benadiha water supply Scheme T/W no - II |  |  | BILL/03288/2023-2024 | BP-2023-24-499 | 05/01/2024 | 05/01/2024 | WBSEDCL | 3.08 | 0 | 0 | 0
Total | [13 empty] | 23322.93 | 430.52 | 1.85