## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS | SM/14995 | New | Material Requisition To Resource Division |  |  | RTOR000107/2022-2023 | 205/MD | 16/01/2023 | 16/01/2023 | Resource Division | 17.35 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS | SM/14995 | New | Sinking of Tube Well ,Laying distribution pipe line, Pump House , Boundary Wall, soil investigation , 300 Cum OHR (Intze type with Pile foundation) & Accommodate FHTC (1946 nos.) under JJM with allied work including 02(Two )Years Operation & Maintenance for Chakabdulla & its adjoining mouzas PWSS in Kharagpur-II Block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000389/2023-2024 | 5063/MD | 26/10/2023 | 13/04/2026 | MIDNAPUR PIPE CONCERN | 522.11 | 250.08 | 47.9 | 55
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS | SM/14995 | New | Material Requisition To Resource Division |  |  | RTOR000076/2024-2025 | 3426/MD | 25/11/2024 | 25/11/2024 | Resource Division | 11.99 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS | SM/14995 | New | Quotation for new power connection at Chak Abdulla PWSS P/H- I , application no - 2004608932 , Ref id - 204222608 |  |  | BILL/04194/2023-2024 | BP-2023-24-769 | 04/03/2024 | 04/03/2024 | WBSEDCL | 2.79 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS | SM/14995 | New | Quotation for new power connection at Chakabdullah PWSS t/w - II , khargpur - II block , Madpur CCC , Application No - 2004799237, Ref ID : 204344491 |  |  | BILL/01635/2024-2025 | BP-2024-25-482 | 30/07/2024 | 30/07/2024 | WBSEDCL | 3.8 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS | SM/14995 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKABDULLA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division-,Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001617/2022-2023 | 498/W/MMD | 20/03/2023 | 02/12/2024 | GOENKA ENTERPRISE | 23.01 | 21.45 | 93.23 | 100
Total | [13 empty] | 581.04 | 271.53 | 46.73