## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS | SM/14996 | New | Sinking of 2 (Two) Nos. Tube well for Chakmaoa & its adjoining mouzas PWSS in Kharagpur-II block including supply of all labour & materials under Kharagpur Sub-Division of Midnapore Division, P.H.E. Dte. in Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE RWS Kharagpur Sub-Division(KGP-II) | ORD/000112/2023-2024 | 2513/MD | 18/07/2023 | 17/08/2023 | FIROJ KHAN | 16.41 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS | SM/14996 | New | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 1361/MD | 02/05/2023 | 02/05/2023 | Resource Division | 20.15 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS | SM/14996 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for CHAKMAOA AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri, Bikas Pramanik, JE, Estimator MMD | ORD/001720/2022-2023 | 618/W/MMD | 20/03/2023 | 16/09/2023 | SUJOY RANJAN BHOWMICK | 21.58 | 0 | 0 | 50
4 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS | SM/14996 | New | Quotation for new power connection at Chakmaoa water supply scheme T/W - II |  |  | BILL/03562/2023-2024 | BP-2023-24-618 | 07/02/2024 | 07/02/2024 | WBSEDCL | 1.99 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Mechanical | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS | SM/14996 | New | Quotation for new power connection at Chakmawa PWSS , T/W - I , Application no - 2004582518 , Ref ID - 204206276 , Madpur CCC |  |  | BILL/03746/2023-2024 | BP-2023-24-705 | 16/02/2024 | 16/02/2024 | WBSEDCL | 3.78 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Kharagpur-II | Midnapore Division | CHAKMAOA AND ITS ADJOINING MOUZAS PWSS | SM/14996 | New | Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 200 Cum OHR (Intze type with Raft foundation) & Accommodate FHTC (837 nos.) under JJM with allied work including supply of all labour & materials for Chakmaoa & its adjoining mouzas PWSS within Kharagpur-II Block including 02 (Two) Years Operation & Maintenance under Kharagpur Sub-Division of Midnapore Division, PHE Dte. in the District of Paschim Medinipur. | AE Kharagpur Sub-division | JE3 Kharagpur Sub-division | ORD/000007/2024-2025 | 1848/MD | 13/06/2024 | 05/12/2025 | DIPAK KUMAR BAKLY | 264.73 | 0 | 0 | 15
Total | [13 empty] | 328.65 | 0 | 0