## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14997 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Chaksadi & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000655/2022-2023 | 1753/MD | 24/08/2022 | 13/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.35 | 3.95 | 90.8 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14997 | New | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 69/MD | 09/01/2023 | 09/01/2023 | Resource Division | 22.68 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14997 | New | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 3357/MD | 25/11/2024 | 25/11/2024 | Resource Division | 10.72 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14997 | New | QUOTATION MONEY FOR CHAKSADI WATER SUPPLY SCHEME, T W NO 1 JJM WORKS, SCHEME CODE SM/14997, APPLICATION NO 2004759795, REFERENCE ID 204321902, BIRSINGHA CCC, WBSEDCL |  |  | BILL/01172/2024-2025 | BP-2024-25-297 | 18/06/2024 | 18/06/2024 | WBSEDCL | 4.43 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14997 | New | QUOTATION MONEY FOR CHAKSADI WATER SUPPLY SCHEME, T W NO 2 JJM WORKS, SCHEME CODE SM/14997, APPLICATION NO 2004759781, REFERENCE ID 204321817, BIRSINGHA CCC, WBSEDCL |  |  | BILL/01173/2024-2025 | BP-2024-25-298 | 18/06/2024 | 18/06/2024 | WBSEDCL | 5.1 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14997 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Chaksadi & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001921/2022-2023 | 840/W/MMD | 24/03/2023 | 20/09/2023 | RITESH ENTERPRISE | 27.39 | 19.55 | 71.38 | 40
Total | [13 empty] | 74.67 | 23.5 | 31.47