## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14998 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001991/2022-2023 | 803/W/MMD | 24/03/2023 | 20/09/2023 | SHREE BISHNU CONSTRUCTION | 10.79 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14998 | New | Laying distribution pipe line under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-D] | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000081/2023-2024 | 2428/MD | 13/07/2023 | 27/08/2023 | MALLICK ENTERPRISE | 9.89 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14998 | New | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | AE Ghatal Sub-division |  | ORD/000661/2022-2023 | 1767/MD | 24/08/2022 | 08/10/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14998 | New | Sinking of 250 X 150 mm dia. X 165 depth Tube well under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-E] | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000015/2023-2024 | 935/MD | 04/04/2023 | 18/04/2023 | MEHER ALI KHAN. | 8.3 | 0 | 0 | 100
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14998 | New | Material Requisition To Resource Division |  |  | RTOR000040/2024-2025 | 3358/MD | 25/11/2024 | 25/11/2024 | Resource Division | 2.94 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14998 | New | QUOTATION MONEY FOR CHAULISINGPUR WATER SUPPLY SCHEME, T W NO I, [ BAHIRSINGPUR ] JJM WORKS, SCHEME CODE SM/14998, APPLICATION NO 2004995144, REFERENCE ID 204465793, GHATAL CCC, WBSEDCL |  |  | BILL/03679/2024-2025 |  | 18/12/2024 | 18/12/2024 | WBSEDCL | 5.23 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14998 | New | Laying distribution pipe line, Rising main & 2 years operation & maintenance under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000080/2023-2024 | 2427/MD | 13/07/2023 | 19/02/2026 | DEVJYOTI BERA | 29.63 | 0 | 0 | 47
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Chaulisingpur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14998 | New | Laying distribution pipe line under JJM with allied work for Chaulisingpur PWSS in Ghatal block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-C] | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000014/2023-2024 | 934/MD | 04/04/2023 | 01/05/2025 | NIMAI HAZRA | 35.97 | 0 | 0 | 100
Total | [13 empty] | 109.49 | 0 | 0