## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | Preparation & Submission of D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed Dwandbipur & its adjoining Mouzas PWSS, Block - Ghatal under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000657/2022-2023 | 1755/MD | 24/08/2022 | 13/09/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 4.94 | 0 | 0 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 62/MD | 09/01/2023 | 09/01/2023 | Resource Division | 19.15 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | Material Requisition To Resource Division |  |  | RTOR000032/2024-2025 | 3359/MD | 25/11/2024 | 25/11/2024 | Resource Division | 13.71 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | DANDIPUR WATER SUPPLY SCHEME, PH - I, BLOCK - GHATAL , SCHEME - SM/14999, REF. ID - 2004496533, GHATAL CCC, |  |  | BILL/03011/2023-2024 | BP-2023-24-393 | 02/12/2023 | 02/12/2023 | WBSEDCL | 3.86 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | DANDIPUR WATER SUPPLY SCHEME, PH - II, BLOCK - GHATAL , SCHEME - SM/14999, REF. ID - 2004496518, GHATAL CCC |  |  | BILL/03012/2023-2024 | BP-2023-24-394 | 02/12/2023 | 02/12/2023 | WBSEDCL | 7.2 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | Sinking of Tube Well, Laying distribution pipe line, Pump House, Boundary Wall, Soil investigation, 300 cum OHR (Intze type with pile foundation) & Accommodate FHTC (2,225 nos.) under JJM with allied work for Dwandbipur PWSS in Ghatal Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Ghatal Sub-Division under Midnapore Division, PHE Dte. | AE Ghatal Sub-division | JE1 Ghatal Sub-division | ORD/000035/2023-2024 | 1337/MD | 28/04/2023 | 28/09/2025 | M/S. D.K.H.CONSTRUCTION | 460.32 | 0 | 0 | 35
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 17/02/2024 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/14999 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Dwandbipur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001614/2022-2023 | 494/W/MMD | 20/03/2023 | 03/11/2025 | J K ENGINEERING CO | 22.96 | 0 | 0 | 100
Total | [13 empty] | 538.75 | 0 | 0