## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GANUA AND ADJOINING MOUJAS PWSS | SM/15000 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Narayangarh Block of Paschim Medinipur District through Jadavpur University. [Name of PWSS: - (1) Ganua, (2) Gokulpur & (3) Naharpur] | AE/RWS Midnapore Sub Division |  | ORD/000709/2022-2023 | 834/MD | 22/03/2023 | 12/04/2023 | JADAVPUR UNIVERSITY | 14.34 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GANUA AND ADJOINING MOUJAS PWSS | SM/15000 | New | Material Requisition To Resource Division |  |  | RTOR000096/2022-2023 | 183/MD | 16/01/2023 | 16/01/2023 | Resource Division | 17.04 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GANUA AND ADJOINING MOUJAS PWSS | SM/15000 | New | Sinking of Tube Well, Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-Soil investigation works for Construction of Over Head Reservoir with laying distribution system, Pump House, Boundary Wall & Providing Functional Household Tap Connection (16,427 Nos.) including 2 years operation & maintenance for BABALPUR, BAHURUPA, BARAKALANKI, GAMA & GANUA Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000238/2023-2024 | 3047/MD | 23/08/2023 | 27/01/2026 | NATIONAL PROJECTS CONSTRUCTION CORPORATION LIMITED | 2411.31 | 0 | 0 | 25
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | GANUA AND ADJOINING MOUJAS PWSS | SM/15000 | New | Material Requisition To Resource Division |  |  | RTOR000114/2024-2025 | 3450/MD | 25/11/2024 | 25/11/2024 | Resource Division | 16.08 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Narayangarh | Central Drilling | GANUA AND ADJOINING MOUJAS PWSS | SM/15000 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
6 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | GANUA AND ADJOINING MOUJAS PWSS | SM/15000 | New | Supply delivery and installation of kit kat fuse carrier for different water supply scheme under Narayangarh Block and others under Midnapore Mechanical Sub Division-I,P.H.E.Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Bikas Pramanik, JE/Midnapur Mechanical Sub-Division | ORD/000368/2024-2025 | 1087/MMSD-I | 06/08/2024 | 21/08/2024 | SOUMEN ELECTRIC | 6.62 | 0 | 0 | 50
Total | [13 empty] | 23805.15 | 0 | 0