## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | GOHALDANGA AND ADJOINING MOUJAS PWSS | SM/15004 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Garhbeta-I, Garhbeta-II & Garhbeta-III Blocks of Paschim Medinipur District through Jadavpur University. [Name of PWSS :- { Garhbeta-I Block - (1) Namjaba (JL.- 822, Plot-556), (2) Shyamnagar (JL.- 619, Plot- 330/1604), (3) Kadra (JL.- 836, Plot-1), (4) Nerasol (JL.- 385, Plot-17), (5) Bhatmara (JL.- 553, Plot-1/534 P), (6) Bagdoba (JL.- 471, Plot-328 P)} {Garhbeta-II Block - (7) Soniakon (JL.- 416, Plot-324), (8) Makli (JL.- 1, Plot-130/345), (9) Kontore (JL.- 163, Plot-156), (10) Keshia (JL.- 150, Plot-41), (11) Bara Bolbandi (JL.- 161, Plot-1/373), (12) Jagardanga (JL.- 208, Plot-4/228), (13) Dumuria (JL.- 89, Plot-178), (14) Gohaldanga (JL.- 288, Plot-17), (15) Kankrisol (JL.- 103, Plot-3/194), (16) Bulanpur (JL.- 66, Plot-5) (17) Bara Kadra (JL.- 138, Plot-6), (18) Amlasuli (JL.- 180, Plot-3), (19) Piasala (JL.- 280, Plot-59), } { Garhbeta-III Block - (20) Kadam Bandhi (JL.- 762, Plot-106), (21) Kantal Diha (JL.- 735, Plot-479/1476), (22) Naya Basat (JL.- 439, Plot-162/486) & (23) Birsinghpur (JL.- 929, Plot-449) }] | AE Sadar Sub-division | JE1 Sadar Sub-division,JE2 Sadar Sub-division | ORD/000650/2022-2023 | 745/MD | 13/03/2023 | 11/06/2023 | JADAVPUR UNIVERSITY | 109.92 | 0 | 0 | 35
2 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | GOHALDANGA AND ADJOINING MOUJAS PWSS | SM/15004 | New | Material Requisition To Resource Division |  |  | RTOR000234/2023-2024 | 1522/MD | 12/05/2023 | 12/05/2023 | Resource Division | 10.33 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | GOHALDANGA AND ADJOINING MOUJAS PWSS | SM/15004 | New | New service connection at Gohaldanga T/W-II water supply scheme. |  |  | BILL/00930/2024-2025 | 327/JMD | 29/08/2024 | 29/08/2024 | WBSEDCL | 3.37 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | GOHALDANGA AND ADJOINING MOUJAS PWSS | SM/15004 | New | New Service connection charges. |  |  | BILL/01357/2023-2024 | 21/JMD | 04/03/2024 | 04/03/2024 | WBSEDCL | 4.68 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | GOHALDANGA AND ADJOINING MOUJAS PWSS | SM/15004 | New | New service connection |  |  | BILL/01298/2023-2024 | 69/JMD | 12/02/2024 | 12/02/2024 | WBSEDCL | 4.49 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | GOHALDANGA AND ADJOINING MOUJAS PWSS | SM/15004 | New | New Service connection charges. |  |  | BILL/01481/2023-2024 | 86/JMD | 21/03/2024 | 21/03/2024 | WBSEDCL | 11.56 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | GOHALDANGA AND ADJOINING MOUJAS PWSS | SM/15004 | New | Construction of 200 Cum capacity R.C.C. Over Head Reservoir over Raft Foundation works with Laying rising main, Distribution system, Sinking of Tube Well, Pump House, Soil investigation, Boundary Wall & Providing Functional Household Tap Connection (1538 Nos.) including Two years operation & maintenance for Gohaldanga Pipe Water Supply Scheme within Garbeta-II Block under Medinipur Sadar Sub-Division of Midnapore Division, PHE Dte. under Paschim Medinipur District. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Garbeta-II) | ORD/000071/2023-2024 | 2152/MD | 08/06/2023 | 04/12/2025 | M/S. D.C.M. CONSTRUCTION | 454.46 | 0 | 0 | 40
8 | PASCHIM MEDINIPUR | Garbeta-II | Central Drilling | GOHALDANGA AND ADJOINING MOUJAS PWSS | SM/15004 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000001/2023-2024 | 1415/CDD | 21/09/2023 | 21/07/2024 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
Total | [13 empty] | 21938.57 | 0 | 0