## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | GOTSHINGLA AND ADJOINING MOUJAS PWSS | SM/15010 | New | Material Requisition To Resource Division |  |  | RTOR000067/2024-2025 | 3390/MD | 25/11/2024 | 25/11/2024 | Resource Division | 3.79 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | GOTSHINGLA AND ADJOINING MOUJAS PWSS | SM/15010 | New | WBSEDCL new connection payment for Goatsingla t/w 1 |  |  | BILL/00093/2024-2025 | 67/JMD | 29/04/2024 | 29/04/2024 | WBSEDCL | 3.68 | 0 | 0 | 0
Total | [13 empty] | 7.47 | 0 | 0