## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | Preparation & Submission of 6 (Six) Nos. D.P.R. along with pipeline Layout Plan, Hy. Design etc. in compliance to JJM guideline for Proposed (1) Shrirampur & its adjoining Mouzas PWSS, (2) Dontiara & its adjoining Mouzas PWSS, (3) Dhashachandpur Mouza Stand Alone PWSS, (4) Udayganj (P) Mouza Stand Alone PWSS, (5) Prasadchak Mouza Stand Alone PWSS AND (6) Anandapur Mouza Stand Alone PWSS, Block - Ghatal under Midnapore Division, PHE Dte. [Name of Proposed PWSS Chaulisingpur & its adjoining Mouzas PWSS & Hemantapur & its adjoining Mouzas PWSS instead of (1) Dhashachandpur Mouza Stand Alone PWSS, (2) Udayganj (P) Mouza Stand Alone PWSS, (3) Prasadchak Mouza Stand Alone PWSS AND (4) Anandapur Mouza Stand Alone PWSS] | AE Ghatal Sub-division |  | ORD/000661/2022-2023 | 1767/MD | 24/08/2022 | 08/10/2022 | SAMARTH INFRA-TECH SERVICES PVT. LTD. | 6.73 | 0.72 | 10.73 | 100
2 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | Material Requisition To Resource Division |  |  | RTOR000137/2022-2023 | 410/MD | 07/02/2023 | 07/02/2023 | Resource Division | 7.2 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | Material Requisition To Resource Division |  |  | RTOR000140/2022-2023 | 410/MD | 07/02/2023 | 07/02/2023 | Resource Division | 7.2 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | CERTIFIED THAT IT IS THE QUOTATION MONEY FOR HEMANTAPUR WATER SUPPLY SCHEME, T W NO 1, JJM WORKS, SCHEME CODE SM/15011, APPLICATION NO 2004627986, REFERENCE ID 204234632, GHATAL CCC, WBSEDCL |  |  | BILL/04400/2023-2024 | BP-2023-24-842 | 14/03/2024 | 14/03/2024 | WBSEDCL | 3.35 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | ADDITIONAL QUOTATION MONEY FOR HEMANTAPUR WATER SUPPLY SCHEME, T W NO I, ADDITIONAL QUOTATION, JJM WORKS, SCHEME CODE SM/15011, APPLICATION NO 100000114253, REFERENCE ID 860308903, GHATAL CCC, WBSEDCL |  |  | BILL/01853/2024-2025 | BP-2024-25-545 | 07/08/2024 | 07/08/2024 | WBSEDCL | 0.73 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001993/2022-2023 | 804/W/MMD | 24/03/2023 | 20/09/2023 | SHREE BISHNU CONSTRUCTION | 10.79 | 10 | 92.62 | 80
7 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Ghatal Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/001825/2023-2024 | 1684/MMSD-I | 19/12/2023 | 17/02/2024 | SUBHASIS ROY | 0.29 | 0 | 0 | 40
8 | PASCHIM MEDINIPUR | Ghatal | Midnapore Mechanical | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Ghatal Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Mahadev Dutta, JE/Midnapur Mechanical Sub-Division- | ORD/002832/2023-2024 | 340/MMSD-I | 05/03/2024 | 05/01/2025 | SUBHASIS ROY | 6.3 | 0 | 0 | 0
9 | PASCHIM MEDINIPUR | Ghatal | Midnapore Division | Hemantapur & its adjoining mouzas Water Supply Scheme, Block - Ghatal, Dist.- Paschim Medinipur. | SM/15011 | New | Laying distribution pipe line & Pump House under JJM with allied work for Hemantapur PWSS in Ghatal Block including supply of all labour & materials within Ghatal Sub-Division under Midnapore Division, PHE Dte. [PART-B] | AE Ghatal Sub-division | JE2 Ghatal Sub-division | ORD/000082/2023-2024 | 2429/MD | 13/07/2023 | 01/01/2025 | JIT ENTERPRISE | 31.13 | 24.95 | 80.13 | 100
Total | [13 empty] | 73.73 | 35.66 | 48.37