## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Garbeta-II | Midnapore Division | KADAM DIHA AND ADJOINING MOUJAS PWSS | SM/15012 | New | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1229/MD | 27/04/2023 | 27/04/2023 | Resource Division | 30.35 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | KADAM DIHA AND ADJOINING MOUJAS PWSS | SM/15012 | New | WBSEDCL new connection payment for Kadamdiha t/w 2 |  |  | BILL/00510/2024-2025 | 228/JMD | 28/06/2024 | 28/06/2024 | WBSEDCL | 7.12 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Garbeta-II | Jhargram Mechanical Division | KADAM DIHA AND ADJOINING MOUJAS PWSS | SM/15012 | New | Payment for WBSEDCL new connection at KADAMDIHA 1 (SM/15012. KADAMDIHA AND ADJOINING MOUJAS PWSS ) |  |  | BILL/00373/2024-2025 | 174/JMD | 07/06/2024 | 07/06/2024 | WBSEDCL | 5.17 | 0 | 0 | 0
Total | [13 empty] | 42.64 | 0 | 0