## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 101/MD | 10/01/2023 | 10/01/2023 | Resource Division | 23.52 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Continuation work order for Hiring of inspection vehicle for supervision & monitoring of different on-going piped water supply scheme for covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission programe. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/001826/2023-2024 | 1685/MMSD-I | 19/12/2023 | 17/02/2024 | M/S BIKASH DE | 0.29 | 0 | 0 | 100
3 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Fuel for Inspection Vehicle of covering Midnapore Sadar Sub-Division and its adjacent Sub-Division under the Dist. of Paschim Medinipur under Jal Jeevan Mission Program. [w.e.f. 01-01-2024 to 29-02-2024] | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002853/2023-2024 | 1698/MMSD-I | 19/12/2023 | 17/02/2024 | M/S BIKASH DE | 0.83 | 0 | 0 | 100
4 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Material Requisition To Resource Division |  |  | RTOR000062/2024-2025 | 3382/MD | 25/11/2024 | 25/11/2024 | Resource Division | 16.98 | 0 | 0 | 0
5 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Electric Quotation bill for Tw No-II of kalagram PWSS. (ref Consumer ID-204128480) |  |  | BILL/02996/2023-2024 | BP-2023-24-388 | 02/12/2023 | 02/12/2023 | WBSEDCL | 3.05 | 0 | 0 | 0
6 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Electric quotation bill for Tw No-I of Kalagram PWSS (Ref Consumer Id-204128489) |  |  | BILL/02995/2023-2024 | BP-2023-24-387 | 02/12/2023 | 02/12/2023 | WBSEDCL | 3.43 | 0 | 0 | 0
7 | PASCHIM MEDINIPUR | Keshpur | Midnapore Division | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Sinking of Tube well, Laying distribution pipe line, Pump House, Boundary wall, Soil investigation, Construction of 400 CuM OHR (Intze type with Pile Foundation) & Accommodate FHTC (2,576 Nos.) under JJM with allied works for Kalagram PWSS in Keshpur Block including supply of all labour & materials including 02 (Two) Years Operation & Maintenance within Midnapur Sadar Sub-Division under Midnapore Division, PHE Dte. | AE Sadar Sub-division | JE RWS Sadar Sub-Division(Keshpur) | ORD/000030/2023-2024 | 947/MD | 06/04/2023 | 30/03/2026 | DULAL CHANDRA DAS | 652.22 | 0 | 0 | 40
8 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. w.e.f.-01-03-2024 to 31-08-2024. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002834/2023-2024 | 339/MMSD-I | 05/03/2024 | 05/01/2025 | M/S BIKASH DE | 6.3 | 0 | 0 | 50
9 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Continuation work order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision & monitoring of different on going piped water supply scheme for covering Midnapore Sadar Sub Division and its adjacent Sub -Division under JJM Programe for the office of Assistant Engineer, under M.M.S.D-I. P.H.E. Dte., Kharagpur , Inda. (Vehicle No. WB 33 C 6546) | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Lab Das, JE/Midnapur Mechanical Sub-Division-I | ORD/002164/2024-2025 | 1826/MMSD-I | 30/12/2024 | 29/06/2025 | M/S BIKASH DE | 3.69 | 0 | 0 | 0
10 | PASCHIM MEDINIPUR | Keshpur | Midnapore Mechanical | KALAGRAM AND ITS ADJOINING MOUZAS PWSS | SM/15013 | New | Providing and Installation of Submersible pumping machineries and other electromechanical equipments for KALAGRAM AND ITS ADJOINING MOUZAS PWSS under JJM Program under MMD PHE Dte. | Sri Bikash Das, AE/Midnapur Mechanical Sub-Division-I | Sri Dablu Dutta, JE/Midnapur Mechanical Sub-Division-I | ORD/001919/2022-2023 | 838/W/MMD | 24/03/2023 | 21/01/2025 | SUJOY RANJAN BHOWMICK | 27.36 | 0 | 0 | 20
Total | [13 empty] | 737.67 | 0 | 0