## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KASHIPUR AND ADJOINING MOUJAS PWSS | SM/15014 | New | Material Requisition To Resource Division |  |  | RTOR000119/2024-2025 | 3455/MD | 25/11/2024 | 25/11/2024 | Resource Division | 16.23 | 0 | 0 | 0
2 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KASHIPUR AND ADJOINING MOUJAS PWSS | SM/15014 | New | Electric quotation for TW-I of Kashipur Water Supply Scheme |  |  | BILL/03360/2023-2024 | BP-2023-24-534 | 11/01/2024 | 11/01/2024 | WBSEDCL | 4.56 | 0 | 0 | 0
3 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Mechanical | KASHIPUR AND ADJOINING MOUJAS PWSS | SM/15014 | New | Electric quotation for TW-II of Kashipur Water Supply Scheme |  |  | BILL/03361/2023-2024 | BP-2023-24-535 | 11/01/2024 | 11/01/2024 | WBSEDCL | 7.91 | 0 | 0 | 0
4 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KASHIPUR AND ADJOINING MOUJAS PWSS | SM/15014 | New | Construction of Different Capacity R.C.C Over Head Reservoir Over Pile / Raft Foundation including Sub-soil investigation works for Construction of Over Head Reservoir with laying distribution system, Sinking of Tube Well, Pump House, Boundary Wall & Providing Functional Household Tap Connection (7130 Nos) including 2 years Operation & Maintenance for Kashipur, Benadiha and Markunda Pipe Water Supply Scheme within Narayangarh Block under Kharagpur Sub-Division of Midnapore Division PHE Dte. under Paschim Medinipur District. | AE Kharagpur Sub-division,Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000126/2023-2024 | 2524/MD | 18/07/2023 | 04/11/2025 | NABA KUMAR BHUNIA | 1870.43 | 567.01 | 30.31 | 82
5 | PASCHIM MEDINIPUR | Narayangarh | Midnapore Division | KASHIPUR AND ADJOINING MOUJAS PWSS | SM/15014 | New | Laying additional quantity of distribution pipeline for providing FHTC at Kashipur, Benadiha & Markunda PWSS under Narayangarh block within Midnapore Division, PHE Dte. | Assistant Engineer (HQ) | JE2 Kharagpur Sub Division | ORD/000180/2024-2025 | 3165/MD | 05/10/2024 | 17/06/2025 | NABA KUMAR BHUNIA | 78.57 | 0 | 0 | 50
Total | [13 empty] | 1977.7 | 567.01 | 28.67